## QUARTER 1
SOUTHERN REGIONAL POWER COMMITTEE THIRD PARTY AUDIT SCHEDULE ¦ QUARTER 1 ¦ April – June 2026
Sl. No | Station(s) to be Audited | Auditee Utility | Nodal Officer(s) Name ¦ Designation Email ¦ Contact | Auditor 1 Name & Designation Utility ¦ Contact ¦ Email | Auditor 2 Name & Designation Utility ¦ Contact ¦ Email | Auditor 3 (In case of Triplet Stations only) Utility ¦ Contact ¦ Email | Period of Audit (Mon – Sat)
1 | 220KV SS Piduguralla 220KV SS Racherlapadu | APTRANSCO | [220KV SS Piduguralla] S. Siva Sankar, EE/MRT&TRF/Guntur eemrtguntur@gmail.com ¦ 9440810962 [220KV SS Racherlapadu] B. Narayana Rao, EE/MRT&TRF/Nellore demrtnellore@gmail.com ¦ 8185041414 | Sunil Kumar K P Asst. Executive Engineer KSEBL Mob: 9446008258 ¦ aeerlyknr@gmail.com | Er. Santoshkumar Joshi EE(E) RT North Division Bangalore KPTCL Mob: 9448365078 ¦ eertdnorth@kptcl.org | N/A (Pair – only 2 auditors) | 20 Apr – 25 Apr 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
2 | 220KV SS Atmakur 220KV SS Mydukur | APTRANSCO | [220KV SS Atmakur] B. Narayana Rao, EE/MRT&TRF/Nellore demrtnellore@gmail.com ¦ 8185041414 [220KV SS Mydukur] J. Rami Reddy, EE/MRT&TRF/Kadapa demrtkdp@gmail.com ¦ 8309600405 | Er. Ragavendra D. EE(E) RT Division Mangalore KPTCL Mob: 9448365084 ¦ eertdmng@kptcl.org | K. Rakesh ADE/MRT/SD/Khammam TGTRANSCO Mob: 9182077839 ¦ rakesh.k11@gmail.com | N/A (Pair – only 2 auditors) | 04 May – 09 May 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
3 | 220KV SS Anrak 220KV SS Bobbili Growth Center | APTRANSCO | [220KV SS Anrak] B. Satyanarayana Reddy, EE/MRT&TRANS/Visakhapatnam eemrtvsp25@gmail.com ¦ 7382933288 [220KV SS Bobbili Growth Center] V. Koteswara Rao, EE/MRT&TRANS/Vijayanagaram demrtvzn@gmail.com ¦ 9440811190 | Er. Shripad Ganapati Hegde EE(E) RT Division Shimoga KPTCL Mob: 9448365083 ¦ eertdsmg@kptcl.org | N. Yashwanth AE/MRT/SD/Budidampadu TGTRANSCO Mob: 9553398212 ¦ aemrtbpdu@gmail.com | N/A (Pair – only 2 auditors) | 04 May – 09 May 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
4 | 220KV SS Kondapuram 400KV SS Rachagunneri | APTRANSCO | [220KV SS Kondapuram] J. Rami Reddy, EE/MRT&TRF/Kadapa demrtkdp@gmail.com ¦ 8309600405 [400KV SS Rachagunneri] Sagili John Wrikley Palestine, EE/O&M/400KV/Chittoor ee400kvonmchittoor@gmail.com ¦ 8328594349 | Er. Ravishankar AEE(E) RT Addl Div Bangalore KPTCL Mob: 9480813813 ¦ eertd.additional@kptcl.org | V. Munusamy AE/GRT/Dharmapuri TANTRANSCO Mob: 9445396910 ¦ aegrtdpi@tnebnet.org | N/A (Pair – only 2 auditors) | 11 May – 16 May 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
5 | 220KV Gadag 220KV Harthi 220kV Ambewadi | KPTCL | [220KV Gadag , Harthi] Er. Ramesh Avanti, EE Operations/Gadag eeoperations.gadag@kptcl.org ¦ 9448271532 [220kV Ambewadi] Er. Prabhakar Y., EE Operations/Sirsi eeoperations.sirsi@kptcl.org ¦ 9448365328 | Sri. C.V. Joshi DEE/400KV/MRT/Manubolu APTRANSCO Mob: 9440811182 ¦ cvjoshiaptransco@gmail.com | K. Harish AE/MRT/400KV GIS Raidurg TGTRANSCO Mob: 9618161780 ¦ harishformula@gmail.com | C. Shyam Sundar AE/CC/Sembatty TANTRANSCO Mob: 9445396831 ¦ aeccsbt@tnebnet.org | 11 May – 16 May 2026 (Mon–Sat) 2 + 2 + 2 days (across 3 stations)
6 | 220kV Hoody 220KV Koramangala | KPTCL | [220kV Hoody] Er. Manjunath, EE Operations/Hoody eeoperations.hoody@kptcl.org ¦ 9448365089 [220KV Koramangala] Er. Anitha, EE Operations/HSR Layout eeoperations.hsr@kptcl.org ¦ 9448365102 | Sri. Yerragudi Jeelan Basha DEE/MRT/400KV/Uravakonda APTRANSCO Mob: 9949207212 ¦ deemrtukd@gmail.com | K.R. Elango AEE/GRT/KR Thoppur TANTRANSCO Mob: 9445396903 ¦ aegrtkrt@tnebnet.org | N/A (Pair – only 2 auditors) | 18 May – 23 May 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
7 | 220kV Channapatna 220kV Haveri | KPTCL | [220kV Channapatna] Er. Keshavamurthy, EE Operations/TK Halli eeoperations.tkhalli@kptcl.org ¦ 9448365240 [220kV Haveri] Er. Vijay Joshi, EE Operations/Haveri eeoperations.haveri@kptcl.org ¦ 9448365335 | Sri. B. Jagadeesh DEE/MRT/Chittor APTRANSCO Mob: 8331031351 ¦ bjs203@gmail.com | K. Baskar AEE/P&C/Hosur TANTRANSCO Mob: 9443792205 ¦ aeepchsr@gmail.com | N/A (Pair – only 2 auditors) | 01 Jun – 06 Jun 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
8 | 400kV Mylasandra 220kV Electronic City | KPTCL | [400kV Mylasandra] Er. Priyadarshini, EE Operations/Mylasandra eeoperations.mylasandra@kptcl.org ¦ 8277943930 [220kV Electronic City] Er. Anitha, EE Operations/HSR Layout eeoperations.hsr@kptcl.org ¦ 9448365102 | C. Manohar Reddy DEE/MRT/SD-3/Madanapally APTRANSCO Mob: 9441416524 ¦ deemrtmpl@gmail.com | M. Thangamani AEE/P&C/S.R. Pudur TANTRANSCO Mob: 9445396869 ¦ aeepcsrpudur@tnebnet.org | N/A (Pair – only 2 auditors) | 08 Jun – 13 Jun 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
9 | 400KV SS Ramadugu 220KV SS Rajeshwaraopet | TGTRANSCO | [400KV SS Ramadugu] [220KV SS Rajeshwaraopet] T. Ramesh, DE/MRT&Trs./Karimnagar de.mrt.knr@tgtransco.com ¦ 8712463462 | P. Nageswara Rao DEE/MRT/Kurnool APTRANSCO Mob: 9440811150 ¦ deemrtknl@gmail.com | Er. C.V. Prakash AEE(E) RT Subdiv Munirabad KPTCL Mob: 9448365014 ¦ aeertpcsd.mrb@kptcl.org | N/A (Pair – only 2 auditors) | 15 Jun – 20 Jun 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
10 | 400KV SS Dindi (Automation) 220KV SS Hayathnagar | TGTRANSCO | [400KV SS Dindi (Automation)] CH. Rama Kanaka Pratap, DE/MRT&TRF/MBNR de.mrt.mbnr@tgtransco.com ¦ 8712463049 [220KV SS Hayathnagar] CH. Sathyanarayana, DE/MRT&T/Fs/Metro-East de.mrt.me@tgtransco.com ¦ 8712462494 | E. Mahesh DEE/MRT/Gooty APTRANSCO Mob: 9490154278 ¦ deemrtgty@gmail.com | Er. Anil Kumar S. AEE(E) RT Subdiv Davanagere KPTCL Mob: 9448365279 ¦ aeertdvg@kptcl.org | N/A (Pair – only 2 auditors) | 27 Apr – 02 May 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
11 | 400kV Vellalaviduthi SS 230kV Poiyur SS | TANTRANSCO | [400kV Vellalaviduthi SS] [230kV Poiyur SS] J. Gunasekaran, AEE/P&C/Thanjavur aepctnj@tnebnet.org ¦ 9445396842 | V.M. Praveen Kumar DEE/400KV/MRT SD-2/Vemagiri APTRANSCO Mob: 9440810927 ¦ deemrtvemagiri@gmail.com | Er. Nandish C. AEE(E) RTD Mysore KPTCL Mob: 9448472395 ¦ eertdmys@kptcl.org | N/A (Pair – only 2 auditors) | 08 Jun – 13 Jun 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
12 | 230kV Ponnapuram SS 400kV Anaikadavu SS | TANTRANSCO | [230kV Ponnapuram SS] [400kV Anaikadavu SS] K. Aramvalarthan, EE/P&C/Coimbatore eepcbe@tnebnet.org ¦ 9445396941 | Kolusu Srinivas DEE/MRT/SD-1/Guntur APTRANSCO Mob: 8333994034 ¦ ademrtgnt@gmail.com | Er. Chandan E. AEE(E) RT Division Hassan KPTCL Mob: 9448090706 ¦ eertdhsn@kptcl.org | N/A (Pair – only 2 auditors) | 15 Jun – 20 Jun 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
13 | 230kV Sadayapalayam SS 230kV Nallamanaickanpatty SS | TANTRANSCO | [230kV Sadayapalayam SS] K. Aramvalarthan, EE/P&C/Coimbatore eepcbe@tnebnet.org ¦ 9445396941 [230kV Nallamanaickanpatty SS] A. Zakir Hussain, EE/P&C/Virudhunagar eepcvdr@tnebnet.org ¦ 9445409681 | Er. Prateek A. Magadam AE(E) RT Division Belgavi KPTCL Mob: 9449596761 ¦ eertdbgm@kptcl.org | K. Indrasena Reddy AE-1/MRT/SD-II/NZB TGTRANSCO Mob: 8712463662 ¦ indra2025@gmail.com | N/A (Pair – only 2 auditors) | 01 Jun – 06 Jun 2026 (Mon–Sat) 3 + 3 days (across 2 stations)
14 | 230kV Kodikurchi SS 220kV Pallivasal Extension PH | TANTRANSCO / KSEBL | [230kV Kodikurchi SS] A. Zakir Hussain, EE/P&C/Tirunelveli eepctin@tnebnet.org ¦ 9445396861 [220kV Pallivasal Extension PH] Anil Kumar T, Executive Engineer eepmdkseb@gmail.com ¦ 9446008578 | J. Emmanuel Anandraj ADE/MRT/SD-III/Metro-West/Hyd TGTRANSCO Mob: 9032936451 ¦ anandrajemmanuel@gmail.com | Er. Harshith B.R. AE(E) RT Division Shimoga KPTCL Mob: 9448092080 ¦ eertdsmg@kptcl.org | N/A (Pair – only 2 auditors) | 11 May – 16 May 2026 (Mon–Sat) 3 +3 days (across 2 stations)

## QUARTER 2
SOUTHERN REGIONAL POWER COMMITTEE THIRD PARTY AUDIT SCHEDULE ¦ QUARTER 2 ¦ July – September 2026
Sl. No | Station(s) to be Audited | Auditee Utility | Nodal Officer(s) Name ¦ Designation ¦ Email ¦ Contact | Auditor 1 Name & Designation Utility ¦ Contact ¦ Email | Auditor 2 Name & Designation Utility ¦ Contact ¦ Email | Auditor 3 (In case of Triplet Stations only) Utility ¦ Contact ¦ Email | Period of Audit (Mon–Sat)
1 | 220KV SS Pulivendula 220KV SS Porumamilla | APTRANSCO | [220KV SS Pulivendula] [220KV SS Porumamilla] J. Rami Reddy, EE/MRT&TRF/Kadapa demrtkdp@gmail.com ¦ 8309600405 | Bijulal V S Asst. Engineer KSEBL Mob: 9447584156 ¦ aeersdt@gmail.com | Er. Ganesh Poojari AEE(E) RT Division Mangalore KPTCL Mob: 9448365440 ¦ eertdmng@kptcl.org | N/A (Pair – 2 auditors only) | 06 Jul – 11 Jul 2026 (Mon–Sat) 3+3 days (2 stations)
2 | 220KV SS Bramhanakotkur 220KV SS Bilakalagudur | APTRANSCO | [220KV SS Bramhanakotkur][220KV SS Bilakalagudur] B. Venu Madhav, EE/MRT&TRF/Kurnool demrtknl@gmail.com ¦ 7901636916 | Er. Paramesh M.K. AEE(E) RT North Division Bangalore KPTCL Mob: 9448999980 ¦ eertdnorth@kptcl.org | M. Venkataiah ADE/MRT/SD-I/Metro Central TGTRANSCO Mob: 8712462433 ¦ mekala_venky57@yahoo.com | N/A (Pair – 2 auditors only) | 13 Jul – 18 Jul 2026 (Mon–Sat) 3+3 days (2 stations)
3 | 220KV SS Vajrakarur 220KV SS Boksampalli | APTRANSCO | [220KV SS Vajrakarur][220KV SS Boksampalli] A. Venkata Giridhar, EE/MRT&Transformers/Ananthapur demrtatp@gmail.com ¦ 9441529981 | Er. Srinivasmurthy N.V. AEE(E) RT North Div Bangalore KPTCL Mob: 9448365114 ¦ eertdnorth@kptcl.org | S. Purnachander AE/MRT/SD/400KV Gajwel TGTRANSCO Mob: 8712462871 ¦ spchand321@gmail.com | N/A (Pair – 2 auditors only) | 20 Jul – 25 Jul 2026 (Mon–Sat) 3+3 days (2 stations)
4 | 400kV Hiremallanhole 220kV Antharasanahally 220kV Hiriyur | KPTCL | [400kV Hiremallanhole] Er. Manjunath N.(I/C), EE Operations/Hiremallanahole eehmhole400kv@kptcl.org ¦ 8277889804 [220kV Antharasanahally] Er. Umesh Hitnal, EE Operations/Tumkur eeoperations.tkr@kptcl.org ¦ 9448365252 [220kV Hiriyur] Er. Riyaz Ahmed, EE Operations/Hiriyur eehiriyur220@kptcl.org ¦ 9448365284 | I. Lakshmi Narayana DEE/MRT/Nellore APTRANSCO Mob: 9490154801 ¦ deemrtnellore@gmail.com | N. Rajalingam ADE/MRT/Sangareddy TGTRANSCO Mob: 8712462796 ¦ rajouce.1218@gmail.com | M. Suresh AEE PC Koyembedu TANTRANSCO Mob: 9445850894 ¦ aeepckbd@tnebnet.org | 27 Jul – 01 Aug 2026 (Mon–Sat) 2+2+2 days (3 stations)
5 | 220kV Guttur SAS 220kV Somasamudra | KPTCL | [220kV Guttur SAS] Er. Mallikarjunappa, EE Operations/Guttur eeguttur400kv@kptcl.org ¦ 9448365267 [220kV Somasamudra] Er. Ayub Basha, EE Operations/Alipur eealipura220@kptcl.org ¦ 9448365467 | R.K. Suman AE CC Korattur TANTRANSCO Mob: 9445396766 ¦ aeegrtktr@tnebnet.org | P. Rajnikanth Reddy ADE/MRT/SD-I/MBNR TGTRANSCO Mob: 8712463057 ¦ ade.mrt.mahabubnagar@gmail.com | N/A (Pair – 2 auditors only) | 03 Aug – 08 Aug 2026 (Mon–Sat) 3+3 days (2 stations)
6 | 220kV Lingasuguru 220kV Yelburga | KPTCL | [220kV Lingasuguru][220kV Yelburga] Er. G.J. Srinivasa, EE Operations/Lingasuru eeoperations.lngsr@kptcl.org ¦ 9448490013 | P. Vara Prasad DEE/MRT SD-2/Vijayawada APTRANSCO Mob: 9494094512 ¦ ademrt2vja@gmail.com | V.S. Padmasankar AEE/P&C/Thalayuthu TANTRANSCO Mob: 9445892711 ¦ aeepctatu@tnebnet.org | N/A (Pair – 2 auditors only) | 17 Aug – 22 Aug 2026 (Mon–Sat) 3+3 days (2 stations)
7 | 220kV Humnabad 220kV Santhpur | KPTCL | [220kV Humnabad] Er. Prabhu Singh H., EE Operations/Humnabad eehmbd220@kptcl.org ¦ 9448365452 [220kV Santhpur] Er. Sujata T.J., EE Operations/Kalaburgi eeoperations.klb@kptcl.org ¦ 9448365448 | N. Veeranjaneyulu DEE/MRT/Simhachalam/Visakhapatnam APTRANSCO Mob: 7382296890 ¦ ademrtvizag@gmail.com | M. Arunkumar AE/GRT/Tenkasi TANTRANSCO Mob: 8695289200 ¦ aegrttks@tnebnet.org | N/A (Pair – 2 auditors only) | 31 Aug – 05 Sep 2026 (Mon–Sat) 3+3 days (2 stations)
8 | 230kV Hosur SS 230kV Udanapalli SS | TANTRANSCO | [230kV Hosur SS][230kV Udanapalli SS] K. Baskar, AEE/P&C/Hosur aeepchsr@gmail.com ¦ 9443792205 | Mallela Kalyan Chakravarthi DEE/MRT/Racharla APTRANSCO Mob: 9490154253 ¦ chakravarthi.mallela@gmail.com | D. Radhakrishna AE/MRT SD-II Wanaparthy TGTRANSCO Mob: 8712463097 ¦ ae.mrt.wanaparthy@gmail.com | N/A (Pair – 2 auditors only) | 03 Aug – 08 Aug 2026 (Mon–Sat) 3+3 days (2 stations)
9 | 230kV Savasapuram SS 230kV S.R.Pudur SS | TANTRANSCO | [230kV Savasapuram SS] A. Zakir Hussain, EE/P&C/Virudhunagar eepcvdr@tnebnet.org ¦ 9445409681 [230kV S.R.Pudur SS] A. Zakir Hussain, EE/P&C/Tirunelveli(I/C) eepctin@tnebnet.org ¦ 9445396861 | Sugali Suresh Babu DEE/MRT/Hindupur APTRANSCO Mob: 8074300091 ¦ ademrthdp@gmail.com | Er. Gopal Krishna H. AEE(E) RT Division Tumkur KPTCL Mob: 9448365275 ¦ eertdtkr@kptcl.org | N/A (Pair – 2 auditors only) | 17 Aug – 22 Aug 2026 (Mon–Sat) 3+3 days (2 stations)
10 | 230kV Tiruchuli SS 230kV Sankaneri SS | TANTRANSCO | [230kV Tiruchuli SS] A. Zakir Hussain, EE/P&C/Virudhunagar eepcvdr@tnebnet.org ¦ 9445409681 [230kV Sankaneri SS] A. Zakir Hussain, EE/P&C/Tirunelveli(I/C) eepctin@tnebnet.org ¦ 9445396861 | Er. Shripad Ganapati Hegde EE(E) RT Division Shimoga KPTCL Mob: 9448365083 ¦ eertdsmg@kptcl.org | C. Bharath DEE/400KV/MRT/Jammalamadugu APTRANSCO Mob: 9491030760 ¦ bharath.transco@gmail.com | N/A (Pair – 2 auditors only) | 31 Aug – 05 Sep 2026 (Mon–Sat) 3+3 days (2 stations)
11 | 220kV Gouridevipally 220kV Singotam | TGTRANSCO | [220kV Gouridevipally][220kV Singotam] CH. Rama Kanaka Pratap, DE/MRT&TRF/MBNR de.mrt.mbnr@tgtransco.com ¦ 8712463049 | P.K. Shivakumar EE/P&C/Trichy TANTRANSCO Mob: 9445396801 ¦ eepctry@tnebnet.org | Er. G. Channa Basavaraj AE(E) RT Subdivision Raichur KPTCL Mob: 9448365482 ¦ aeertrcr@kptcl.org | N/A (Pair – 2 auditors only) | 07 Sep – 12 Sep 2026 (Mon–Sat) 3+3 days (2 stations)
12 | 400/220KV Julurupadu 220KV LIS BGKothuru | TGTRANSCO | [400/220KV Julurupadu][220KV LIS BGKothuru] S. Anjaiah, DE/MRT&TRF/KMM de.mrt.khmm@tgtransco.com ¦ 8712463363 | Amalchith V A Asst. Engineer KSEBL Mob: 9946665441 ¦ aeersdklsy@gmail.com | Er. Chandan E. AEE(E) RT Division Hassan KPTCL Mob: 9448090706 ¦ eertdhsn@kptcl.org | N/A (Pair – 2 auditors only) | 21 Sep – 26 Sep 2026 (Mon–Sat) 3+3 days (2 stations)
13 | 220/11KV SS Markook 400/11KV SS Tukkapur | TGTRANSCO | [220/11KV SS Markook][400/11KV SS Tukkapur] K. Chennaiah, DE/MRT&Transformers/Sangareddy de.mrt.srd@tgtransco.com ¦ 8712462769 | Er. Madam Nagaraja AE(E) RT Division Chitradurga KPTCL Mob: 9480813898 ¦ eertdcta@kptcl.org | R.S. Sankar AEE/P&C/Salem TANTRANSCO Mob: 9445396904 ¦ aeepcslm@tnebnet.org | N/A (Pair – 2 auditors only) | 21 Sep – 26 Sep 2026 (Mon–Sat) 3+3 days (2 stations)
14 | 220kV Areacode SS 220kV Palakkad SS | KSEBL | [220kV Areacode SS][220kV Palakkad SS] Biju M.T, Executive Engineer eerdknr@gmail.com ¦ 9446008256 | Er. Satish K. AEE(E) RT Division Mangalore KPTCL Mob: 8277892686 ¦ eertdmng@kptcl.org | K. Srikanth ADE/Shift/Ramagundam TGTRANSCO Mob: 9948918625 ¦ srikanth273@yahoo.com | N/A (Pair – 2 auditors only) | 07 Sep – 12 Sep 2026 (Mon–Sat) 3+3 days (2 stations)

## QUARTER 3
SOUTHERN REGIONAL POWER COMMITTEE THIRD PARTY AUDIT SCHEDULE ¦ QUARTER 3 ¦ October – December 2026
Grp No | Station(s) to be Audited | Auditee Utility | Nodal Officer(s) Name ¦ Designation ¦ Email ¦ Contact | Auditor 1 Name & Designation Utility ¦ Contact ¦ Email | Auditor 2 Name & Designation Utility ¦ Contact ¦ Email | Auditor 3 (Triplet only) | Period of Audit (Mon–Sat)
1 | 220kV Hebbal 220kV Manyatha GIS | KPTCL | [220kV Hebbal] [220kV Manyatha GIS] Er. Roseline Smitha, EE Operations/Hebbal eeoperations.hebbal@kptcl.org ¦ 9448365101 | Seepana Bhaskar Rao DEE/MRT SD-1/Srikakulam APTRANSCO Mob: 9490155045 ¦ deemrtsklm@gmail.com | SK. Fayaz Assistant Engineer TGGENCO Mob: 8500908179 ¦ ktps7.deem@tggenco.com | N/A (Pair – 2 auditors only) | 05 Oct – 10 Oct 2026 (Mon–Sat) 3+3 days (2 stations)
2 | 220kV KIADB Hardware Park 220kV Haraluru Muddenahalli | KPTCL | [220kV KIADB Hardware Park] Er. Prakash M., EE Operations/BIAL Begur eeoperations.bialbegur@kptcl.org ¦ 9449596742 [220kV Haraluru Muddenahalli] Er. Laxman S.G., EE Operations/Doddaballapura eeoperations.dbp@kptcl.org ¦ 9448365243 | M. Anjinaiah DEE/400KV/MRT SD-2/Narnoor APTRANSCO Mob: 9491050636 ¦ anjinaiah.m@aptransco.gov.in | R. Venkat Reddy AE-1/TRE & Protn./NZB TGTRANSCO Mob: 8712463678 ¦ venkat.ramadgu543@gmail.com | N/A (Pair – 2 auditors only) | 12 Oct – 17 Oct 2026 (Mon–Sat) 3+3 days (2 stations)
3 | 400KV Nelamangala 220kV Nagarabhavi | KPTCL | [400KV Nelamangala] Er. Poornima C., EE Operations/Nelamangala eeoperations.nmangla@kptcl.org ¦ 9448365087 [220kV Nagarabhavi] Er. Jyothi G.R., EE Operations/NRS Rajajinagar eeoperations.nrs@kptcl.org ¦ 9448365104 | R. Anitha ADE/MRT/400KV GISS Raidurg TGTRANSCO Mob: 9949652715 ¦ ade.mrt.raidurg@gmail.com | S. Hariskumar AE GRT Korattur TANTRANSCO Mob: 9445396763 ¦ aeegrtktr@tnebnet.org | N/A (Pair – 2 auditors only) | 26 Oct – 31 Oct 2026 (Mon–Sat) 3+3 days (2 stations)
4 | 220kV Mahalingapur 220kV Basarkod | KPTCL | [220kV Mahalingapur] Er. Jayaprakash G. Patil, EE Operations/Bagalkote eemahalingapur220@kptcl.org ¦ 9448365301 [220kV Basarkod] Er. Wahid Jahagirdar, EE Operations/Vijaypura eeoperations.bjp@kptcl.org ¦ 9448365298 | Bunga Praneeth DEE/MRT/Kakinada APTRANSCO Mob: 7382294420 ¦ praneeth.bunga@aptransco.co.in | R. Gokul AE GRT SP Koil TANTRANSCO Mob: 9445892698 ¦ aeepcspkl@tnebnet.org | N/A (Pair – 2 auditors only) | 02 Nov – 07 Nov 2026 (Mon–Sat) 3+3 days (2 stations)
5 | Ranganathapuram 230kV SS Nokia 230kV SS Omega 230kV SS | TANTRANSCO | [Ranganathapuram 230kV SS] M. Senthilkumar, EE/P&C/Madurai eepcmdu@tnebnet.org ¦ 9445396821 [Nokia 230kV SS] M. Neelakandan, EE/P&C/Sriperumpudur(I/C) eepcspr@tnebnet.org ¦ 9445396745 | V. Murali Krishna DEE/400KV/MRT/Maradam APTRANSCO Mob: 9490155068 ¦ deemrtmaradam@gmail.com | Aneesh Babu Asst. Executive Engineer KSEBL Mob: 9446008234 ¦ aeersdktr@gmail.com | Er. M. Veeresh Kumar EE(E) RT Division Bellary KPTCL Mob: 9448365080 ¦ eertdballari@kptcl.org | 09 Nov – 14 Nov 2026 (Mon–Sat) 2+2+2 days (3 stations)
6 | Pasumalai 230kV SS Samayanallur 230kV SS | TANTRANSCO | [Pasumalai 230kV SS][Samayanallur 230kV SS] M. Senthilkumar, EE/P&C/Madurai eepcmdu@tnebnet.org ¦ 9445396821 | Gorja Appala Naidu DEE/MRT/SD-1/Pendurthy APTRANSCO Mob: 8639173407 ¦ ademrtpdt.aptransco@gmail.com | Er. Ambika R. EE(E) RT Division Hassan KPTCL Mob: 9448090693 ¦ eertdhsn@kptcl.org | N/A (Pair – 2 auditors only) | 16 Nov – 21 Nov 2026 (Mon–Sat) 3+3 days (2 stations)
7 | Kurukathi 230kV SS Pallakapalayam 230kV SS | TANTRANSCO | [Kurukathi 230kV SS][Pallakapalayam 230kV SS] K. Muruganandam, EE/P&C/Erode eepced@tnebnet.org ¦ 9445396921 | M. Suresh ADE/Automation/Karimnagar TGTRANSCO Mob: 8712463459 ¦ ade.autm&it.knr@tgtransco.com | Er. Punith Kumar K. AEE(E) RT Division Kolar KPTCL Mob: 8277889803 ¦ eertdkolar@kptcl.org | N/A (Pair – 2 auditors only) | 30 Nov – 05 Dec 2026 (Mon–Sat) 3+3 days (2 stations)
8 | 220KV SS Inaparajupalli SW 220KV SS Pallantla | APTRANSCO | [220KV SS Inaparajupalli SW] S. Siva Sankar, EE/MRT&TRF/Guntur eemrtguntur@gmail.com ¦ 9440810962 [220KV SS Pallantla] B. Naga Bhushanam, EE/MRT&TRANS/Eluru demrteluru@gmail.com ¦ 9440810961 | Er. Raghunandan S.R. AEE(E) RT Division Shimoga KPTCL Mob: 9886796947 ¦ eertdsmg@kptcl.org | B. Vilas AE/MRT/Manchiryal TGTRANSCO Mob: 8712463745 ¦ vilas.b203@gmail.com | N/A (Pair – 2 auditors only) | 05 Oct – 10 Oct 2026 (Mon–Sat) 3+3 days (2 stations)
9 | 220KV SS Bommuru 220KV SS Duvva | APTRANSCO | [220KV SS Bommuru] K. Vijaya Kumar, EE/MRT&TRANS/Rajahmundry demrttrfaptranscorjy@gmail.com ¦ 9440811033 [220KV SS Duvva] B. Naga Bhushanam, EE/MRT&TRANS/Eluru demrteluru@gmail.com ¦ 9440810961 | Er. Pampanagowda AEE(E) RT Division Bellary KPTCL Mob: 9448365480 ¦ eertdballari@kptcl.org | M. Sarvotham Reddy ADE/MRT/Nirmal TGTRANSCO Mob: 8712463731 ¦ msreddy.3007@gmail.com | N/A (Pair – 2 auditors only) | 12 Oct – 17 Oct 2026 (Mon–Sat) 3+3 days (2 stations)
10 | 220KV SS Markapur 220KV SS Parchur | APTRANSCO | [220KV SS Markapur][220KV SS Parchur] K. Satya Prasad, EE/MRT&TRF/Ongole demrtongole@gmail.com ¦ 9154162538 | Er. Rakesh Kulkarni AEE(E) RT Division Hubballi KPTCL Mob: 9448365356 ¦ eertdhbl@kptcl.org | G. Prabhakar AEE P&C Sunguvarchatram TANTRANSCO Mob: 9445396765 ¦ aeepncsvchatram@tnebnet.org | N/A (Pair – 2 auditors only) | 26 Oct – 31 Oct 2026 (Mon–Sat) 3+3 days (2 stations)
11 | 220/11KV SS Gangaram 220/11KV Sarangapur | TGTRANSCO | [220/11KV SS Gangaram] B. Ravindra, DE/MRT&TFRS/Warangal de.mrt.wgl@tgtransco.com ¦ 8712463206 [220/11KV Sarangapur] P. Narender Reddy, DE/MRT&Trs/Nizamabad(FAC) adekmr61031@gmail.com ¦ 8712463646 | S. Loganathan AEE/P&C/Coimbatore TANTRANSCO Mob: 9445867859 ¦ aeepccbe@tnebnet.org | R. Murugesh AE/GRT/Kayathar TANTRANSCO Mob: 9445396863 ¦ aegrtkyr@tnebnet.org | N/A (Pair – 2 auditors only) | 02 Nov – 07 Nov 2026 (Mon–Sat) 3+3 days (2 stations)
12 | 220/132/33KV SS Jangaon 220/11KV Mentrajpally 220KV SS Medaram | TGTRANSCO | [220/132/33KV SS Jangaon] B. Ravindra, DE/MRT&TFRS/Warangal de.mrt.wgl@tgtransco.com ¦ 8712463206 [220/11KV Mentrajpally] P. Narender Reddy, DE/MRT&Trs/Nizamabad(FAC) adekmr61031@gmail.com ¦ 8712463646 [220KV SS Medaram] M. Srinivas, DE/MRT/Ramagundam de.mrt.rdm@tgtransco.com ¦ 8712463577 | Er. Narendrakumar AE(E) RT Division Kalaburagi KPTCL Mob: 9538565092 ¦ eertdklb@kptcl.org | A. Zakir Hussain EE/P&C/VDR TANTRANSCO Mob: 9445409681 ¦ eepcvdr@tnebnet.org | Abhilash A Asst. Executive Engineer KSEBL Mob: 9446008260 ¦ aeerlyksd@gmail.com | 07 Dec – 12 Dec 2026 (Mon–Sat) 2+2+2 days (3 stations)
13 | KTPS-VII Stage 220KV SS Vemnur | TGTRANSCO / TGGENCO | [KTPS-VII Stage] V. Chandra Mouly, Divisional Engineer ktps7.deem@tggenco.com ¦ 9490612583 [220KV SS Vemnur] M. Srinivas, DE/MRT/Ramagundam de.mrt.rdm@tgtransco.com ¦ 8712463577 | P. Anil Kumar DEE/400KV/MRT/Tallayapalem APTRANSCO Mob: 9440811175 ¦ deemrt400kvgistlpm@gmail.com | Er. Sunil Kumar K. AE(E) RT Division Mandya KPTCL Mob: 8277893635 ¦ eertdmandya@kptcl.org | N/A (Pair – 2 auditors only) | 14 Dec – 19 Dec 2026 (Mon–Sat) 3+3 days (2 stations)
14 | 220kV Pothencode SS 220kV Pathanamthitta GIS SS | KSEBL | [220kV Pothencode SS][220kV Pathanamthitta GIS SS] Jyothikumar(I/C), Executive Engineer eerdtvm@gmail.com ¦ 9446008029 | A. Prasad ADE/MRT SD/Jagityal TGTRANSCO Mob: 8712463493 ¦ ade.mrt.jgl@tgtransco.com | N. Natarajan AE/GRT/P&C-1/Trichy TANTRANSCO Mob: 8220170564 ¦ aeepc1try@tnebnet.org | N/A (Pair – 2 auditors only) | 30 Nov – 05 Dec 2026 (Mon–Sat) 3+3 days (2 stations)

## QUARTER 4
SOUTHERN REGIONAL POWER COMMITTEE THIRD PARTY AUDIT SCHEDULE ¦ QUARTER 4 ¦ January – March 2027
Grp No | Station(s) to be Audited | Auditee Utility | Nodal Officer(s) Name ¦ Designation ¦ Email ¦ Contact | Auditor 1 Name & Designation Utility ¦ Contact ¦ Email | Auditor 2 Name & Designation Utility ¦ Contact ¦ Email | Auditor 3 (Triplet only) | Period of Audit (Mon–Sat)
1 | 220KV SS Chittoor 220KV SS Palamaneru | APTRANSCO | [220KV SS Chittoor][220KV SS Palamaneru] Madiri. Surendra Naidu, EE/MRT&TRF/Tirupathi demrttlstpt@gmail.com ¦ 9490404163 | T.D. Mathanlal AEE/P&C/Sembatty TANTRANSCO Mob: 9445396830 ¦ aeepcsbt@tnebnet.org | P. Srikanth AE-1/MRT/Karimnagar TGTRANSCO Mob: 8500600581 ¦ Srikanth.rpg88@gmail.com | N/A (Pair – 2 auditors only) | 04 Jan – 09 Jan 2027 (Mon–Sat) 3+3 days (2 stations) | 44
2 | 220KV SS Shapuram 220KV SS Gollapuram | APTRANSCO | [220KV SS Shapuram][220KV SS Gollapuram] A. Venkata Giridhar, EE/MRT&Transformers/Ananthapur demrtatp@gmail.com ¦ 9441529981 | A. Joshwa AE/CC/Thalaiyuthu TANTRANSCO Mob: 9445892712 ¦ aegrttatu@tnebnet.org | C. Rajasekhar Reddy ADE/MRT/SD-II/Metro-East TGTRANSCO Mob: 8712462515 ¦ ade2.mrt.me@tgtransco.com | N/A (Pair – 2 auditors only) | 18 Jan – 23 Jan 2027 (Mon–Sat) 3+3 days (2 stations)
3 | 220KV SS Nansuralla 220KV Gooty RS | APTRANSCO | [220KV SS Nansuralla] B. Venu Madhav, EE/MRT&TRF/Kurnool demrtknl@gmail.com ¦ 7901636916 [220KV Gooty RS] A. Venkata Giridhar, EE/MRT&Transformers/Ananthapur demrtatp@gmail.com ¦ 9441529981 | Er. Nagaraj T. AEE(E) RT South Division Bangalore KPTCL Mob: 9448365077 ¦ eertdsouth@kptcl.org | J.S. Abilash AEE/PC/Checkanurani TANTRANSCO Mob: 9445396825 ¦ aeepccki@tnebnet.org | N/A (Pair – 2 auditors only) | 01 Feb – 06 Feb 2027 (Mon–Sat) 3+3 days (2 stations)
4 | 220kV Kunnamkulam SS 220kV New Pallom | KSEBL | [220kV Kunnamkulam SS][220kV New Pallom] Rajesh K, Executive Engineer eerdklsy@gmail.com ¦ 9446008241 | K. Yedukondalu DEE/MRT/Podili APTRANSCO Mob: 9491030017 ¦ ademrtpodili@gmail.com | Er. Chand Basha AEE(E) RT Circle Kalaburagi KPTCL Mob: 9739778548 ¦ eertdklb@kptcl.org | N/A (Pair – 2 auditors only) | 08 Feb – 13 Feb 2027 (Mon–Sat) 3+3 days (2 stations)
5 | 400kV Hebbanahally 220kV Hootagally | KPTCL | [400kV Hebbanahally] Er. Prasanna (I/C), EE 400kV Operations/Hassan eeoperations.hbnhalli@kptcl.org ¦ 9448998048 [220kV Hootagally] Er. Harshakumar H.M., EE Operations/Hootagalli eeoperations.htgly@kptcl.org ¦ 9448365372 | Marri Suresh Vidyasagar DEE/MRT SD-1/Rajahmundry APTRANSCO Mob: 7032877272 ¦ sureshvsagar.m@aptransco.co.in | M. Prashanth ADE/Maint/400KV SS Jangaon TGTRANSCO Mob: 8712463238 ¦ ade400kvjangaon@gmail.com | N/A (Pair – 2 auditors only) | 04 Jan – 09 Jan 2027 (Mon–Sat) 3+3 days (2 stations)
6 | 220kV Bannur 220kV Tubinakere | KPTCL | [220kV Bannur] Er. Bhimappa A. Dandeppanavar, EE Ops/Belagavi eeoperations.bgm@kptcl.org ¦ 9448365344 [220kV Tubinakere] Er. Y.N. Santhosh Kumar, EE Operations/Mandya eeoperations.mandya@kptcl.org ¦ 9448365368 | Jansha M Asst. Executive Engineer KSEBL Mob: 9446008257 ¦ aeerlyshr@gmail.com | S. Arun AE/GRT/P&C/Trichy TANTRANSCO Mob: 9445396803 ¦ aeepc2try@tnebnet.org | N/A (Pair – 2 auditors only) | 18 Jan – 23 Jan 2027 (Mon–Sat) 3+3 days (2 stations)
7 | 220kV Nagamanagala 220kV Dudda | KPTCL | [220kV Nagamanagala] Er. Y.N. Santhosh Kumar, EE Operations/Mandya eeoperations.mandya@kptcl.org ¦ 9448365368 [220kV Dudda] Er. Prasanna, EE Operations/Hassan eeoperations.hsn@kptcl.org ¦ 9448365376 | Kopala Govinda Raju DEE/MRT SD-3/Rayachoti APTRANSCO Mob: 9490154246 ¦ Deemrtryct@gmail.com | S.N. Paneerselvam AEE/P&C/Palladam TANTRANSCO Mob: 9445060610 ¦ aeepcpldm@tnebnet.org | N/A (Pair – 2 auditors only) | 01 Feb – 06 Feb 2027 (Mon–Sat) 3+3 days (2 stations)
8 | 220kV Srinivasapura 220kV Kanagala | KPTCL | [220kV Srinivasapura] Er. Srinath S., EE Operations/Kolar eeoperations.kolar@kptcl.org ¦ 9448365247 [220kV Kanagala] Er. Vijayakumar Kole, EE Operations/Chikkodi eeoperations.chikkodi@kptcl.org ¦ 9448365293 | R. Anjaneyulu Naik DEE/TRE & Protection/Vizianagaram APTRANSCO Mob: 9440811209 ¦ adetrevzm@gmail.com | A. Mahendramani AEE/P&C/Kundha TANTRANSCO Mob: 9445396962 ¦ aeepckun@tnebnet.org | N/A (Pair – 2 auditors only) | 08 Feb – 13 Feb 2027 (Mon–Sat) 3+3 days (2 stations)
9 | 220/33kV SS HIAL 220/132/33kV SS Shamshabad | TGTRANSCO | [220/33kV SS HIAL][220/132/33kV SS Shamshabad] CH. Sathyanarayana, DE/MRT&T/Fs/Metro-East de.mrt.me@tgtransco.com ¦ 8712462494 | Er. Veena M. EE(E) RT Division Mysore KPTCL Mob: 9448365085 ¦ eertdmys@kptcl.org | R. Krishnaraj AE/GRT/Thiruvarur TANTRANSCO Mob: 9445396846 ¦ aegrttrvr@tnebnet.org | N/A (Pair – 2 auditors only) | 15 Feb – 20 Feb 2027 (Mon–Sat) 3+3 days (2 stations)
10 | 220/132/33kV SS Chandanvally 400/220/132kV SS Kethireddypally LJHES | TGTRANSCO / TGGENCO | [220/132/33kV SS Chandanvally] V. Kashiram Bapuji, DE/MRT&Trfs./Metro-West/Hyd de.mrt.mw@tgtransco.com ¦ 8712462605 [LJHES] S. Roopesh Kumar, DE/O&M lj.deom@tggenco.com ¦ 8500784150 | Vijayakumar K Executive Engineer NLCIL Mob: 9791499120 ¦ vijayakumark@nlcindia.in | Er. Venugopal AEE(E) RT Subdivision Munirabad KPTCL Mob: 9448365483 ¦ aeertrmrb@kptcl.org | C. Shanmugam AEE/P&C/Dharmapuri TANTRANSCO Mob: 9445396909 ¦ aeepcdpi@tnebnet.org | 01 Mar – 06 Mar 2027 (Mon–Sat) 3+2+1 days (3 stations)
11 | 220/11kV Mupkal 220/132/33kV SS Nirmal | TGTRANSCO | [220/11kV Mupkal] P. Narender Reddy, DE/MRT&Trs/Nizamabad(FAC) adekmr61031@gmail.com ¦ 8712463646 [220/132/33kV SS Nirmal] M. Naga Thirumala, DE/MRT&Trs/Adilabad de.mrt.adb@tgtransco.com ¦ 8712463427 | Er. Rangaswamy B.N. AE(E) RT Division Mandya KPTCL Mob: 8277893657 ¦ eertdmandya@kptcl.org | D. Obuliraj AEE/P&C/KR Thoppur TANTRANSCO Mob: 9445396902 ¦ aeepckrt@tnebnet.org | N/A (Pair – 2 auditors only) | 22 Feb – 27 Feb 2027 (Mon–Sat) 3+3 days (2 stations)
12 | Guindy 400KV SS Alandur CMRL 230kV SS Koyambedu GIS SS 230kV | TANTRANSCO | [Guindy 400KV SS][Alandur CMRL 230kV SS][Koyambedu GIS SS 230kV] S. Kumar, EE/P&C/Guindy eepcgnd@tnebnet.org ¦ 9445892693 | P. Imdad Basha DEE/MRT/400KV SS/Rachagunneri APTRANSCO Mob: 9440811142 ¦ imdadbasha.p@aptransco.gov.in | Er. Sapna R. AEE(E) RT North Division Bangalore KPTCL Mob: 9448365115 ¦ eertdnorth@kptcl.org | P. Vijay Kumar ADE/MRT/SD-III/Warangal TGTRANSCO Mob: 8712463246 ¦ ademrtsd3wgl@gmail.com | 15 Feb – 20 Feb 2027 (Mon–Sat) 2+2+2 days (3 stations)
13 | Basin Bridge 230kV SS Central CMRL 230kV SS NLC TS1 220kV Switch yard | TANTRANSCO | [Basin Bridge 230kV SS][Central CMRL 230kV SS] K. Navin Kumar, EE/P&C-1/Chennai ee1pcchn@tnebnet.org ¦ 9445396721 [TS1 220kV Switch yard] S. Dixon Joel, Executive Engineer dixonjoel.s@nlcindia.in ¦ 9600644393 | Er. Jayappa Wali AEE(E) RT Subdivision Vijayapur KPTCL Mob: 9448365359 ¦ aeertsd.bjp@kptcl.org | T. Rajeshwar Rao ADE/Main/SD/Gangaram TGTRANSCO Mob: 8712463218 ¦ rajeshwar0806@gmail.com | G. Venkateswara Rao DEE/MRT SD-1/Eluru APTRANSCO Mob: 9490155128 ¦ venkat.guthula@aptransco.co.in | 22 Feb – 27 Feb 2027 (Mon–Sat) 2+2+2 days (3 stations)
14 | Ambattur 3rd Main Road 230kV SS Thiruverkadu 230kV SS | TANTRANSCO | [Ambattur 3rd Main Road 230kV SS][Thiruverkadu 230kV SS] R. Rajasekar, EE/P&C/Korattur eepcktr@tnebnet.org ¦ 9445396761 | L. Rajender ADE/MRT/SD-I/Warangal TGTRANSCO Mob: 8712463229 ¦ ademrtsd1wgl@gmail.com | B. Sathya Prakash Reddy AE/PJHES TGGENCO Mob: 9491564032 ¦ pj.deom@tggenco.com | N/A (Pair – 2 auditors only) | 08 Mar – 13 Mar 2027 (Mon–Sat) 3+3 days (2 stations)
15 | Vysarpadi 230kV SS Ottiyampakkam 400KV SS | TANTRANSCO / NLCIL | [Vysarpadi 230kV SS] R. Rajasekar, EE/P&C/Korattur eepcktr@tnebnet.org ¦ 9445396761 [Ottiyampakkam 400KV SS] S. Kumar, EE/P&C/Guindy eepcgnd@tnebnet.org ¦ 9445892693 | Er. Mallappa Golabhavi S. AE(E) RT Division Bagalakote KPTCL Mob: 8277895832 ¦ eertd.bgkt@kptcl.org | A. Lakshmaiah ADE/MRT/Nalgonda TGTRANSCO Mob: 9440376927 ¦ laksman.aitharaju@gmail.com | N/A (Pair – 2 auditors only) | 22 Mar – 27 Mar 2027 (Mon–Sat) 3+3 days (2 stations)