## CGS
Unitwise planned maintenance 2026-27 approved by MoP/CEA
Central Generating Units
Month | Station | Unit | MW | From | To | No of Days | Remarks
2026-04-01 | KAIGA | 1 | 220 | 2026-04-01 | 2026-09-30 | 183 | EMCCR
| MADRAS A.P.S. | 1 | 220 | 2026-04-01 | 2027-03-31 | 365 | under project mode
2026-05-01 | NIL
2026-06-01 | TELANGANA STPP | 2 | 800 | 2026-06-01 | 2026-07-11 | 41 | Boiler + Generator OH ( B type inspection) With Rotor removal + TG auxilary
| NEYVELI TPS-II | 4 | 210 | 2026-06-01 | 2026-07-05 | 35 | Statutory Boiler Inspection,RLA, Boiler, Turbine short shutdown works
| NEYVELI TPS-II EXP | 1 | 250 | 2026-06-01 | 2026-06-30 | 30 | AOH - Annual Overhaul of Boiler, Turbine and Generator and its auxilliaries
| NTPL TUTICORIN | 1 | 500 | 2026-06-05 | 2026-06-11 | 7 | Boiler License Renewal
| RAMAGUNDEM STPS | 5 | 500 | 2026-06-08 | 2026-07-10 | 33 | Boiler O/H +LPT + Gen OH
| TALCHER STPS | 6 | 500 | 2026-06-10 | 2026-07-14 | 35 | Overhaul
2026-07-01 | NEYVELI NEW TPP | 1 | 500 | 2026-07-01 | 2026-08-14 | 45 | Unit-1 Major Overhauling Works
| NEYVELI TPS-II | 2 | 210 | 2026-07-07 | 2026-08-10 | 35 | Statutory Boiler Inspection, RLA, Boiler, Turbine short shutdown works
| KUDGI STPP | 1 | 800 | 2026-07-16 | 2026-09-13 | 60 | COH
| VALLUR TPP | 2 | 500 | 2026-07-13 | 2026-08-26 | 45 | COH
2026-08-01 | NEYVELI TPS-II | 5 | 210 | 2026-08-12 | 2026-09-25 | 45 | Statutory Boiler Inspection, Turbine MOH
| VALLUR TPP | 3 | 500 | 2026-08-26 | 2026-08-30 | 5 | Boiler License Renewal
2026-09-01 | NEYVELI NEW TPP | 2 | 500 | 2026-09-01 | 2026-09-10 | 10 | Boiler Statutory Inspection
| NEYVELI ( EXT) TPS | 2 | 210 | 2026-09-11 | 2026-10-05 | 25 | Annual Maintenance: Overhauling of Motors BFP A, ID fan A & FD fan B.,RAPH 1 & 2 Inspection Rectification work,ESP Reconditioning,ABG 1 complete chain replacement, ABG 2 Rectification work,SSC 1 Reconditioning,of Switch yard & Unit Electrical equipments such as 400 KV CT, CVT, Breakers & Isolaters, Transformers, HVRT, HT &LT motors, HT&LT Switch gears, Valves, Dampers, UPS & Battery charger
| NEYVELI TPS-II | 3 | 210 | 2026-09-27 | 2026-10-31 | 35 | Statutory Boiler Inspection, Boiler, Turbine short shutdown works
2026-10-01 | RAMAGUNDEM STPS | 1 | 200 | 2026-10-01 | 2026-10-30 | 30 | Boiler O/H + Unit Aux + Gen OH
| KUDGI STPP | 3 | 800 | 2026-10-01 | 2026-11-29 | 60 | COH
| NEYVELI ( EXT) TPS | 1 | 210 | 2026-10-07 | 2026-10-31 | 25 | Annual Maintenance: Unit Electrical equipments such as 400 KV CT, CVT,Breakers & Isolaters, Transformers, HVRT, HT &LT motors, HT&LT Switch gears, Valves, Dampers, UPS & Battery charger ESP Reconditioning,RAPH 1 inpsection and rectification works, RAPH2 Complete basket replacement,ABG Inspection and rectification., Reconditioning works of ID fans HAD,Mill & PF ducts repair works and Defective Nozzle repair work.,Boiler drum Inspection/Safety valve R/C work.,Eco, SH & RH Coil cleaning work.
| SIMHADRI | 4 | 500 | 2026-10-15 | 2026-11-19 | 36 | Boiler, TG Aux, and Gen OH
| VALLUR TPP | 1 | 500 | 2026-10-26 | 2026-10-30 | 5 | Boiler License Renewal
2026-11-01 | RAMAGUNDEM STPS | 7 | 500 | 2026-11-01 | 2026-12-05 | 35 | Boiler O/H + Unit Aux + Gen OH
| NEYVELI TPS-II | 6 | 210 | 2026-11-02 | 2026-12-06 | 35 | Statutory Boiler Inspection, Boiler, Turbine short shutdown works
| NEYVELI TPS-II EXP | 2 | 250 | 2026-11-03 | 2027-03-31 | 149 | Capital Overhaul of Turbine and Generator, along with Major FBHE Modification
| KAIGA | 4 | 220 | 2026-11-10 | 2026-12-19 | 40 | BSD
| SIMHADRI | 2 | 500 | 2026-11-21 | 2027-01-09 | 50 | Boiler, HPT, IPT & TG Aux, Gen OH and DCS R&M
2026-12-01 | NTPL TUTICORIN | 2 | 500 | 2026-12-01 | 2026-12-30 | 30 | Annual Maintenance
| NEYVELI TPS-II | 1 | 210 | 2026-12-08 | 2027-01-11 | 35 | Statutory Boiler Inspection, Boiler, Turbine short shutdown works
| KAIGA | 2 | 220 | 2026-12-21 | 2027-01-29 | 40 | BSD
| TALCHER STPS | 5 | 500 | 2026-12-25 | 2027-01-28 | 35 | Overhaul
2027-01-01 | MADRAS A.P.S. | 2 | 220 | 2027-01-01 | 2027-03-31 | 90 | Long shutdown for major upgradation in primary and secondary circuit components for a period of 18 months from 01.01.2027
| KUDANKULAM | 1 | 1000 | 2027-01-08 | 2027-02-27 | 51 | RSD-9 (Refueling Shutdown)
| NEYVELI TPS-II | 7 | 210 | 2027-01-13 | 2027-02-16 | 35 | Statutory Boiler Inspection, Boiler, Turbine short shutdown works
2027-02-01 | NIL
2027-03-01 | NIL
ISTS connected IPPs
Month | Station | Unit | MW | From | To | No of Days | Remarks
2026-04-01 | NIL
2026-05-01 | NIL
2026-06-01 | ITPCL TPP | 1 | 600 | 2026-06-01 | 2026-06-30 | 30 | AOH
| THAMMINAPATNAM TPS (MEL) | 1 | 150 | 2026-06-01 | 2026-06-09 | 9 | For Annual Inspection of Boiler
| PAINAMPURAM TPP (SEIL P-I) | 2 | 660 | 2026-06-20 | 2026-07-15 | 26 | AOH
2026-07-01 | MUTHIARA TPP (MPGL) | 2 | 600 | 2026-07-15 | 2026-08-29 | 46 | COH
2026-08-01 | NIL
2026-09-01 | ITPCL TPP | 2 | 600 | 2026-09-01 | 2026-09-30 | 30 | AOH
| SGPL TPP (SEIL P-II) | 1 | 660 | 2026-09-15 | 2026-10-29 | 45 | COH
| THAMMINAPATNAM TPS (MEL) | 3 | 350 | 2026-09-20 | 2026-09-28 | 9 | For Annual Inspection of Boiler
2026-10-01 | MUTHIARA TPP (MPGL) | 1 | 600 | 2026-10-01 | 2026-11-15 | 46 | COH
| SIMHAPURI TPS | 2 | 150 | 2026-10-20 | 2026-11-25 | 37 | AOH
| THAMMINAPATNAM TPS (MEL) | 4 | 350 | 2026-10-20 | 2026-10-28 | 9 | For Annual Inspection of Boiler
2026-11-01 | NIL
2026-12-01 | SIMHAPURI TPS | 4 | 150 | 2026-12-01 | 2026-12-31 | 31 | AOH
2027-01-01 | THAMMINAPATNAM TPS (MEL) | 2 | 150 | 2027-01-02 | 2027-01-10 | 9 | For Annual Inspection of Boiler
2027-02-01 | NIL
2027-03-01 | NIL
APGENCO units and STU connected IPPs
Month | Station | Unit | MW | From | To | No. of Days | Remarks
2026-04-01 | NIL
2026-05-01 | NIL
2026-06-01 | Dr. N.TATA RAO TPS | 5 | 210 | 2026-06-15 | 2026-06-30 | 16 | Annual Overhaul
| Dr. N.TATA RAO TPS | 3 | 210 | 2026-06-20 | 2026-07-05 | 16 | Annual Overhaul
2026-07-01 | Dr. N.TATA RAO TPS | 1 | 210 | 2026-07-01 | 2026-07-15 | 15 | Annual Overhaul
| RAYALASEEMA TPS | 6 | 600 | 2026-07-01 | 2026-07-20 | 20 | Annual Overhaul
| RAYALASEEMA TPS | 1 | 210 | 2026-07-10 | 2026-07-25 | 16 | Annual Overhaul
| Dr. N.TATA RAO TPS | 8 | 800 | 2026-07-19 | 2026-08-09 | 22 | Annual Overhaul
2026-08-01 | VIZAG TPP (HNPCL) | 2 | 520 | 2026-08-01 | 2026-08-16 | 16 | Boiler open inspection & Overhaul works
2026-09-01 | NIL
2026-10-01 | Dr. N.TATA RAO TPS | 4 | 210 | 2026-10-15 | 2026-10-30 | 16 | Annual Overhaul
2026-11-01 | Dr. N.TATA RAO TPS | 2 | 210 | 2026-11-01 | 2026-11-15 | 15 | Annual Overhaul
| RAYALASEEMA TPS | 2 | 210 | 2026-11-05 | 2026-11-20 | 16 | Annual Overhaul
| DAMODARAM SANJEEVAIAH TPS | 1 | 800 | 2026-11-10 | 2026-11-30 | 21 | Annual Overhaul
| VIZAG TPP (HNPCL) | 1 | 520 | 2026-11-10 | 2026-12-25 | 46 | Capital Overhaul
| RAYALASEEMA TPS | 4 | 210 | 2026-11-20 | 2026-12-05 | 16 | Annual Overhaul
2026-12-01 | DAMODARAM SANJEEVAIAH TPS | 2 | 800 | 2026-12-01 | 2026-12-25 | 25 | Annual Overhaul
| RAYALASEEMA TPS | 3 | 210 | 2026-12-10 | 2026-12-25 | 16 | Annual Overhaul
| Dr. N.TATA RAO TPS | 6 | 210 | 2026-12-16 | 2026-12-30 | 15 | Annual Overhaul
2027-01-01 | RAYALASEEMA TPS | 5 | 210 | 2027-01-01 | 2027-01-15 | 15 | Annual Overhaul
| Dr. N.TATA RAO TPS | 7 | 500 | 2027-01-05 | 2027-01-25 | 21 | Annual Overhaul
| DAMODARAM SANJEEVAIAH TPS | 3 | 800 | 2027-01-10 | 2027-01-30 | 21 | Annual Overhaul
2027-02-01 | NIL
2027-03-01 | NIL
KPCL and STU connected IPPs
Month | Station | Unit | MW | From | To | No of Days | Remarks
2026-04-01 | RAICHUR TPS | 1 | 210 | 2026-04-01 | 2027-03-31 | Long shut down | Long shut down
2026-05-01 | NIL
| BELLARY TPS | 2 | 500 | 2026-06-01 | 2026-07-31 | 61 | COH/ RLA of TG
2026-06-01 | RAICHUR TPS | 3 | 210 | 2026-06-01 | 2026-09-19 | 111 | R & M of Turbine & Generator and MOH
| TORANGALLU TPS(SBU-I) | 1 | 130 | 2026-06-03 | 2026-06-17 | 15 | AOH
| TORANGALLU TPS(SBU-II) | 3 | 300 | 2026-06-10 | 2026-11-27 | 171 | Boiler R&M works & COH
| YERMARUS TPP | 1 | 800 | 2026-06-11 | 2026-07-10 | 30 | AOH
| TORANGALLU TPS(SBU-II) | 4 | 300 | 2026-06-18 | 2026-07-02 | 15 | AOH
2026-07-01 | RAICHUR TPS | 7 | 210 | 2026-07-05 | 2026-07-30 | 26 | AOH
2026-08-01 | BELLARY TPS | 1 | 500 | 2026-08-16 | 2026-09-05 | 21 | AOH
2026-09-01 | RAICHUR TPS | 6 | 210 | 2026-09-01 | 2026-10-31 | 61 | MOH of Turbine & Generator and replacement of Boiler economiser Coil
| UDUPI TPP | 2 | 600 | 2026-09-01 | 2026-10-05 | 35 | COH
| RAICHUR TPS | 2 | 210 | 2026-09-05 | 2026-09-30 | 26 | AOH
| BELLARY TPS | 3 | 700 | 2026-09-15 | 2026-10-05 | 21 | AOH
2026-10-01 | NIL
2026-11-01 | YERMARUS TPP | 2 | 800 | 2026-11-01 | 2026-11-30 | 30 | AOH
| RAICHUR TPS | 5 | 210 | 2026-11-01 | 2026-11-26 | 26 | AOH
2026-12-01 | RAICHUR TPS | 8 | 250 | 2026-12-01 | 2026-12-26 | 26 | AOH
| RAICHUR TPS | 4 | 210 | 2026-12-05 | 2026-12-30 | 26 | AOH
2027-01-01 | NIL
2027-02-01 | NIL
2027-03-01 | NIL
TNPGCL units and STU connected IPPs
Month | Station | Unit | MW | From | To | No. of Days | Remarks
2026-04-01 | NIL
2026-05-01 | NIL
2026-06-01 | NEYVELI TPS(Z) | 1 | 250 | 2026-06-02 | 2026-06-07 | 6 | R&M activities
| VALUTHUR CCPP | 4 | 32.4 | 2026-06-05 | 2026-06-14 | 10 | Renewal of Boiler Licence and Its allied works of HRSG
2026-07-01 | TUTICORIN TPS | 2 | 210 | 2026-07-16 | 2026-08-04 | 20 | AOH
| NORTH CHENNAI TPS | 5 | 600 | 2026-07-26 | 2026-09-23 | 60 | CAPITAL OVERHAUL
2026-08-01 | METTUR TPS | 1 | 210 | 2026-08-01 | 2026-08-15 | 15 | AOH
| NORTH CHENNAI TPS | 1 | 210 | 2026-08-01 | 2026-08-30 | 30 | AOH
| METTUR TPS | 4 | 210 | 2026-08-16 | 2026-09-30 | 46 | COH
| TUTICORIN TPS | 1 | 210 | 2026-08-17 | 2026-09-05 | 20 | AOH
| NEYVELI TPS(Z) | 1 | 250 | 2026-08-28 | 2026-09-17 | 21 | Annual maintenance
2026-09-01 | NORTH CHENNAI TPS | 2 | 210 | 2026-09-01 | 2026-09-30 | 30 | AOH
| KUTTALAM CCPP | 1 | 63 | 2026-09-01 | 2026-09-15 | 15 | Combustion Inspection Works
| TUTICORIN TPS | 3 | 210 | 2026-09-11 | 2026-10-05 | 25 | AOH
2026-10-01 | TUTICORIN TPS | 4 | 210 | 2026-10-01 | 2026-11-14 | 45 | COH
| METTUR TPS - II | 1 | 600 | 2026-10-01 | 2026-11-19 | 50 | COH
| NORTH CHENNAI TPS | 3 | 210 | 2026-10-01 | 2026-10-30 | 30 | AOH
2026-11-01 | METTUR TPS | 3 | 210 | 2026-11-01 | 2026-11-15 | 15 | AOH
| TUTICORIN TPS | 5 | 210 | 2026-11-16 | 2026-12-30 | 45 | COH
| NORTH CHENNAI TPS | 4 | 600 | 2026-11-16 | 2026-12-30 | 45 | ANNUAL OVERHAUL
2026-12-01 | METTUR TPS | 2 | 210 | 2026-12-01 | 2026-12-15 | 15 | AOH
| TUTICORIN TPP ST-IV (SEPC) | 1 | 525 | 2026-12-20 | 2027-01-10 | 22 | AOH
2027-01-01 | NIL
2027-02-01 | NIL
2027-03-01 | NIL
TGGENCO units and STU connected IPPs
Month | Station | Unit | MW | From | To | No. of Days | Remarks
2026-04-01 | NIL
2026-05-01 | NIL
2026-06-01 | KAKATIYA TPS | 1 | 500 | 2026-06-01 | 2026-07-15 | 45 | COH
| SINGARENI TPP | 2 | 600 | 2026-06-16 | 2026-07-21 | 36 | AOH
| BHADRADRI TPP | 1 | 270 | 2026-06-18 | 2026-07-07 | 20 | AOH
2026-07-01 | KOTHAGUDEM TPS (NEW) | 10 | 250 | 2026-07-10 | 2026-07-29 | 20 | AOH
| YADADRI TPS | 1 | 800 | 2026-07-12 | 2026-07-31 | 20 | AOH
2026-08-01 | NIL
2026-09-01 | NIL
2026-10-01 | NIL
2026-11-01 | YADADRI TPS | 4 | 800 | 2026-11-01 | 2026-11-20 | 20 | AOH
| KAKATIYA TPS | 2 | 600 | 2026-11-15 | 2026-12-04 | 20 | AOH
| BHADRADRI TPP | 4 | 270 | 2026-11-21 | 2026-12-10 | 20 | AOH
2026-12-01 | YADADRI TPS | 3 | 800 | 2026-12-01 | 2026-12-20 | 20 | AOH
2027-01-01 | NIL
2027-02-01 | NIL
2027-03-01 | NIL
Puducherry units
Month | Station | Unit | MW | From | To | No. of Days | Remarks
2026-06-01 | KARAIKAL CCPP | 1 | 32.5 | 2026-06-02 | 2026-06-13 | 12 | Boiler License Renewal
2026-12-01 | KARAIKAL CCPP | 1 | 32.5 | 2026-12-15 | 2027-01-31 | 48 | GT Major Inspection and maintenance

## ISTS conn IPPs
ISTS connected IPPs
Month | Station | Unit | MW | From | To | No of Days | Remarks
2026-04-01 | NIL
2026-05-01 | NIL
2026-06-01 | ITPCL TPP | 1 | 600 | 2026-06-01 | 2026-06-30 | 30 | AOH
| THAMMINAPATNAM TPS (MEL) | 1 | 150 | 2026-06-01 | 2026-06-09 | 9 | For Annual Inspection of Boiler
| PAINAMPURAM TPP (SEIL P-I) | 2 | 660 | 2026-06-20 | 2026-07-15 | 26 | AOH
2026-07-01 | MUTHIARA TPP (MPGL) | 2 | 600 | 2026-07-15 | 2026-08-29 | 46 | COH
2026-08-01 | NIL
2026-09-01 | ITPCL TPP | 2 | 600 | 2026-09-01 | 2026-09-30 | 30 | AOH
| SGPL TPP (SEIL P-II) | 1 | 660 | 2026-09-15 | 2026-10-29 | 45 | COH
| THAMMINAPATNAM TPS (MEL) | 3 | 350 | 2026-09-20 | 2026-09-28 | 9 | For Annual Inspection of Boiler
2026-10-01 | MUTHIARA TPP (MPGL) | 1 | 600 | 2026-10-01 | 2026-11-15 | 46 | COH
| SIMHAPURI TPS | 2 | 150 | 2026-10-20 | 2026-11-25 | 37 | AOH
| THAMMINAPATNAM TPS (MEL) | 4 | 350 | 2026-10-20 | 2026-10-28 | 9 | For Annual Inspection of Boiler
2026-11-01 | NIL
2026-12-01 | SIMHAPURI TPS | 4 | 150 | 2026-12-01 | 2026-12-31 | 31 | AOH
2027-01-01 | THAMMINAPATNAM TPS (MEL) | 2 | 150 | 2027-01-02 | 2027-01-10 | 9 | For Annual Inspection of Boiler
2027-02-01 | NIL
2027-03-01 | NIL

## Andhra Pradesh
APGENCO units and STU connected IPPs
Month | Station | Unit | MW | From | To | No. of Days | Remarks
2026-04-01 | NIL
2026-05-01 | NIL
2026-06-01 | Dr. N.TATA RAO TPS | 5 | 210 | 2026-06-15 | 2026-06-30 | 16 | Annual Overhaul
| Dr. N.TATA RAO TPS | 3 | 210 | 2026-06-20 | 2026-07-05 | 16 | Annual Overhaul
2026-07-01 | Dr. N.TATA RAO TPS | 1 | 210 | 2026-07-01 | 2026-07-15 | 15 | Annual Overhaul
| RAYALASEEMA TPS | 6 | 600 | 2026-07-01 | 2026-07-20 | 20 | Annual Overhaul
| RAYALASEEMA TPS | 1 | 210 | 2026-07-10 | 2026-07-25 | 16 | Annual Overhaul
| Dr. N.TATA RAO TPS | 8 | 800 | 2026-07-19 | 2026-08-09 | 22 | Annual Overhaul
2026-08-01 | VIZAG TPP (HNPCL) | 2 | 520 | 2026-08-01 | 2026-08-16 | 16 | Boiler open inspection & Overhaul works
2026-09-01 | NIL
2026-10-01 | Dr. N.TATA RAO TPS | 4 | 210 | 2026-10-15 | 2026-10-30 | 16 | Annual Overhaul
2026-11-01 | Dr. N.TATA RAO TPS | 2 | 210 | 2026-11-01 | 2026-11-15 | 15 | Annual Overhaul
| RAYALASEEMA TPS | 2 | 210 | 2026-11-05 | 2026-11-20 | 16 | Annual Overhaul
| DAMODARAM SANJEEVAIAH TPS | 1 | 800 | 2026-11-10 | 2026-11-30 | 21 | Annual Overhaul
| VIZAG TPP (HNPCL) | 1 | 520 | 2026-11-10 | 2026-12-25 | 46 | Capital Overhaul
| RAYALASEEMA TPS | 4 | 210 | 2026-11-20 | 2026-12-05 | 16 | Annual Overhaul
2026-12-01 | DAMODARAM SANJEEVAIAH TPS | 2 | 800 | 2026-12-01 | 2026-12-25 | 25 | Annual Overhaul
| RAYALASEEMA TPS | 3 | 210 | 2026-12-10 | 2026-12-25 | 16 | Annual Overhaul
| Dr. N.TATA RAO TPS | 6 | 210 | 2026-12-16 | 2026-12-30 | 15 | Annual Overhaul
2027-01-01 | RAYALASEEMA TPS | 5 | 210 | 2027-01-01 | 2027-01-15 | 15 | Annual Overhaul
| Dr. N.TATA RAO TPS | 7 | 500 | 2027-01-05 | 2027-01-25 | 21 | Annual Overhaul
| DAMODARAM SANJEEVAIAH TPS | 3 | 800 | 2027-01-10 | 2027-01-30 | 21 | Annual Overhaul
2027-02-01 | NIL
2027-03-01 | NIL

## Karnataka
KPCL and STU connected IPPs
Month | Station | Unit | MW | From | To | No of Days | Remarks
2026-04-01 | RAICHUR TPS | 1 | 210 | 2026-04-01 | 2027-03-31 | Long shut down | Long shut down
2026-05-01 | NIL
| BELLARY TPS | 2 | 500 | 2026-06-01 | 2026-07-31 | 61 | COH/ RLA of TG
2026-06-01 | RAICHUR TPS | 3 | 210 | 2026-06-01 | 2026-09-19 | 111 | R & M of Turbine & Generator and MOH
| TORANGALLU TPS(SBU-I) | 1 | 130 | 2026-06-03 | 2026-06-17 | 15 | AOH
| TORANGALLU TPS(SBU-II) | 3 | 300 | 2026-06-10 | 2026-11-27 | 171 | Boiler R&M works & COH
| YERMARUS TPP | 1 | 800 | 2026-06-11 | 2026-07-10 | 30 | AOH
| TORANGALLU TPS(SBU-II) | 4 | 300 | 2026-06-18 | 2026-07-02 | 15 | AOH
2026-07-01 | RAICHUR TPS | 7 | 210 | 2026-07-05 | 2026-07-30 | 26 | AOH
2026-08-01 | BELLARY TPS | 1 | 500 | 2026-08-16 | 2026-09-05 | 21 | AOH
2026-09-01 | RAICHUR TPS | 6 | 210 | 2026-09-01 | 2026-10-31 | 61 | MOH of Turbine & Generator and replacement of Boiler economiser Coil
| UDUPI TPP | 2 | 600 | 2026-09-01 | 2026-10-05 | 35 | COH
| RAICHUR TPS | 2 | 210 | 2026-09-05 | 2026-09-30 | 26 | AOH
| BELLARY TPS | 3 | 700 | 2026-09-15 | 2026-10-05 | 21 | AOH
2026-10-01 | NIL
2026-11-01 | YERMARUS TPP | 2 | 800 | 2026-11-01 | 2026-11-30 | 30 | AOH
| RAICHUR TPS | 5 | 210 | 2026-11-01 | 2026-11-26 | 26 | AOH
2026-12-01 | RAICHUR TPS | 8 | 250 | 2026-12-01 | 2026-12-26 | 26 | AOH
| RAICHUR TPS | 4 | 210 | 2026-12-05 | 2026-12-30 | 26 | AOH
2027-01-01 | NIL
2027-02-01 | NIL
2027-03-01 | NIL

## Tamil Nadu
TNPGCL units and STU connected IPPs
Month | Station | Unit | MW | From | To | No. of Days | Remarks
2026-04-01 | NIL
2026-05-01 | NIL
2026-06-01 | NEYVELI TPS(Z) | 1 | 250 | 2026-06-02 | 2026-06-07 | 6 | R&M activities
| VALUTHUR CCPP | 4 | 32.4 | 2026-06-05 | 2026-06-14 | 10 | Renewal of Boiler Licence and Its allied works of HRSG
2026-07-01 | TUTICORIN TPS | 2 | 210 | 2026-07-16 | 2026-08-04 | 20 | AOH
| NORTH CHENNAI TPS | 5 | 600 | 2026-07-26 | 2026-09-23 | 60 | CAPITAL OVERHAUL
2026-08-01 | METTUR TPS | 1 | 210 | 2026-08-01 | 2026-08-15 | 15 | AOH
| NORTH CHENNAI TPS | 1 | 210 | 2026-08-01 | 2026-08-30 | 30 | AOH
| METTUR TPS | 4 | 210 | 2026-08-16 | 2026-09-30 | 46 | COH
| TUTICORIN TPS | 1 | 210 | 2026-08-17 | 2026-09-05 | 20 | AOH
| NEYVELI TPS(Z) | 1 | 250 | 2026-08-28 | 2026-09-17 | 21 | Annual maintenance
2026-09-01 | NORTH CHENNAI TPS | 2 | 210 | 2026-09-01 | 2026-09-30 | 30 | AOH
| KUTTALAM CCPP | 1 | 63 | 2026-09-01 | 2026-09-15 | 15 | Combustion Inspection Works
| TUTICORIN TPS | 3 | 210 | 2026-09-11 | 2026-10-05 | 25 | AOH
2026-10-01 | TUTICORIN TPS | 4 | 210 | 2026-10-01 | 2026-11-14 | 45 | COH
| METTUR TPS - II | 1 | 600 | 2026-10-01 | 2026-11-19 | 50 | COH
| NORTH CHENNAI TPS | 3 | 210 | 2026-10-01 | 2026-10-30 | 30 | AOH
2026-11-01 | METTUR TPS | 3 | 210 | 2026-11-01 | 2026-11-15 | 15 | AOH
| TUTICORIN TPS | 5 | 210 | 2026-11-16 | 2026-12-30 | 45 | COH
| NORTH CHENNAI TPS | 4 | 600 | 2026-11-16 | 2026-12-30 | 45 | ANNUAL OVERHAUL
2026-12-01 | METTUR TPS | 2 | 210 | 2026-12-01 | 2026-12-15 | 15 | AOH
| TUTICORIN TPP ST-IV (SEPC) | 1 | 525 | 2026-12-20 | 2027-01-10 | 22 | AOH
2027-01-01 | NIL
2027-02-01 | NIL
2027-03-01 | NIL

## Telangana
TGGENCO units and STU connected IPPs
Month | Station | Unit | MW | From | To | No. of Days | Remarks
2026-04-01 | NIL
2026-05-01 | NIL
2026-06-01 | KAKATIYA TPS | 1 | 500 | 2026-06-01 | 2026-07-15 | 45 | COH
| SINGARENI TPP | 2 | 600 | 2026-06-16 | 2026-07-21 | 36 | AOH
| BHADRADRI TPP | 1 | 270 | 2026-06-18 | 2026-07-07 | 20 | AOH
2026-07-01 | KOTHAGUDEM TPS (NEW) | 10 | 250 | 2026-07-10 | 2026-07-29 | 20 | AOH
| YADADRI TPS | 1 | 800 | 2026-07-12 | 2026-07-31 | 20 | AOH
2026-08-01 | NIL
2026-09-01 | NIL
2026-10-01 | NIL
2026-11-01 | YADADRI TPS | 4 | 800 | 2026-11-01 | 2026-11-20 | 20 | AOH
| KAKATIYA TPS | 2 | 600 | 2026-11-15 | 2026-12-04 | 20 | AOH
| BHADRADRI TPP | 4 | 270 | 2026-11-21 | 2026-12-10 | 20 | AOH
2026-12-01 | YADADRI TPS | 3 | 800 | 2026-12-01 | 2026-12-20 | 20 | AOH
2027-01-01 | NIL
2027-02-01 | NIL
2027-03-01 | NIL

## Puducherry
Puducherry units
Month | Station | Unit | MW | From | To | No. of Days | Remarks
2026-06-01 | KARAIKAL CCPP | 1 | 32.5 | 2026-06-02 | 2026-06-13 | 12 | Boiler License Renewal
2026-12-01 | KARAIKAL CCPP | 1 | 32.5 | 2026-12-15 | 2027-01-31 | 48 | GT Major Inspection and maintenance