## CGS & ISTS Connected
Unit Outages Approved in 238th OCC
|  |  |  | As per MoP Plan |  |  |  | Revised Proposal by Entity
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Remarks
NTPC / NTECL Units
1 | TELANGANA STPP | 2 | 800 | 2026-06-01 | 2026-07-11 | 41 | Boiler + Generator OH ( B type inspection) With Rotor removal + TG auxilary |  |  |  | NTPC Vide mail dtd 21.04.2026 furnished a revised proposal, in which TSTPP 1 is chosen in place of TSPP 2. 238th OCC: NTPC confirmed the outage of Unit 2 will not be availed in this FY. Further, due to peak demand season, on TGSLDC request to postpone to 10th June, Telangana STPP yet to confirm the same. Forum suggested to avail at the earliest.
2 | TELANGANA STPP | 1 | 800 |  |  |  | Boiler + Generator-B with Rotor Thread out | 2026-06-01 | 2026-07-10 | 40
3 | RAMAGUNDEM STPS | 5 | 500 | 2026-06-08 | 2026-07-10 | 33 | Boiler O/H +LPT + Gen OH | 2026-08-15 | 2026-09-28 | 45 | 238th OCC: As per the revised proposal furnished by NTPC, this outage will be discussed in the upcoming OCC (239)
4 | TALCHER STPS | 6 | 500 | 2026-06-10 | 2026-07-14 | 35 | Overhaul |  |  |  | NTPC Vide mail dtd 21.04.2026 furnished a revised proposal. 238th OCC: Forum approved the same & suggested to stick on the scheduled timelines.
5 | NTPC RAMAGUNDAM | 3 | 200 |  |  |  | Boiler+ Generator +TG bearing and Valves | 2026-06-15 | 2026-07-14 | 30 | NTPC Vide mail dtd 21.04.2026 furnished a fresh proposal. 238th OCC: Forum approved the same & suggested to stick on the scheduled timelines.
6 | NTPC Talcher | 3 | 500 |  |  |  | condenser liability, new addition to COS list | 2026-07-16 | 2026-08-04 | 20 | NTPC Vide mail dtd 21.04.2026 furnished a fresh proposal from 20th July 2026. 238th OCC: Based on TG request, Forum approved from 16th July & suggested to revive at the earliest.
7 | NTPC KUDGI | 1 | 800 | 2026-07-16 | 2026-09-13 | 60 | COH (Boiler+ Turbine + Generator) | 2026-08-17 | 2026-10-15 | 60 | NTPC Vide mail dtd 21.04.2026 furnished a revised proposal from 17th Aug for 60 days. 238th OCC: Forum suggested to avail from 15th July. However OEM & material supply issues, NTPC can't avail in July month. As per the beneficiaries request, not to facilitate during high irrigation loads, this outage would be discussed in the next OCC.
8 | NTECL Vallur | 2 | 500 | 2026-07-13 | 2026-08-26 | 45 | COH (Boiler+ Turbine + Generator) | 2026-06-12 | 2026-07-23 | 42 | NTPC Vide mail dtd 21.04.2026 furnished a revised proposal from 12th June for 42 days. 238th OCC: Forum approved the same & suggested to stick on with the approved schedule.
NLCIL/NTPL Units
1 | NEYVELI TPS-II | 4 | 210 | 2026-06-01 | 2026-07-05 | 35 | Statutory Boiler Inspection,RLA, Boiler, Turbine short shutdown works | 2026-07-15 | 2026-08-18 | 35 | 238th OCC: TPS II is requested to condense the outage duration to 30 days instead of 35 days & share the revised proposal
2 | NEYVELI TPS-II EXP | 1 | 250 | 2026-06-01 | 2026-06-30 | 30 | AOH - Annual Overhaul of Boiler, Turbine and Generator and its auxilliaries | 2026-08-01 | 2026-08-30 | 30 | 238th OCC: Due to non-availability of critical contracts, requested to postpone to 01st August for 30 days. This will be discussed in the upcoming OCC (239)
3 | NTPL TUTICORIN | 1 | 500 | 2026-06-05 | 2026-06-11 | 7 | Boiler License Renewal | 2026-07-05 | 2026-08-03 | 30 | Actual dates proposed by NTPL was 05.07.2026 (for 30 days). After study, unit outage is proposed on 15.08.2026 for 30 days. 238th OCC: NTPL Tuticorin agreed to avail from August month. This will be discussed in the upcoming OCC (239)
4 | NEYVELI TPS-II | 2 | 210 | 2026-07-07 | 2026-08-10 | 35 | Statutory Boiler Inspection, RLA, Boiler, Turbine short shutdown works | 2026-08-19 | 2026-09-22 | 35 | 238th OCC: As per the revised proposal furnished by TPS II, this outage will be discussed in the upcoming OCC (239)
5 | NEYVELI TPS-II | 1 | 210 | 2026-12-08 | 2027-01-11 | 35 | Statutory Boiler Inspection, Boiler, Turbine short shutdown works | 2026-05-06 | 2026-06-09 | 35 | 238th OCC: As per MoP guidelines, no unit outage is allowed to approve in the month of May 2026. Also TPS II is requested to condense the outage duration to 30 days instead of 35 days & share the revised proposal
6 | NEYVELI TPS-II | 3 | 210 | 2026-09-27 | 2026-10-31 | 35 | Statutory Boiler Inspection, Boiler, Turbine short shutdown works | 2026-06-10 | 2026-07-14 | 35 | 238th OCC: TPS II is requested to condense the outage duration to 30 days instead of 35 days & share the revised proposal
7 | NNTPS | 2 | 500 | 2026-09-01 | 2026-09-10 | 10 | Boiler Statutory Inspection | 2026-07-28 | 2026-08-06 | 10 | 238th OCC: Sticking on to the actual plan.
8 | NNTPS | 1 | 500 | 2026-07-01 | 2026-08-14 | 45 | Major Overhauling Works | 2026-08-08 | 2026-09-11 | 35 | 238th OCC:As per the revised proposal furnished by NNTPP, this outage will be discussed in the upcoming OCC (239)
238th OCC : NLCIL vide mail dtd 31.03.2026 & NTPL vide 07.04.2026 had shared the revised proposal. NLCIL is requested to furnish the revised schedule for all the units. A) one TPS II unit at a time without overlap B) Rest all units of NLCIL (TPS I Exp, TPS II Exp, NNTPS & NTPL) without any overlap at the earliest.
NPCIL Units
1 | KAIGA | 1 | 220 | 2026-04-01 | 2026-09-30 | 183 | EMCCR
2 | MADRAS A.P.S. | 1 | 220 | 2026-04-01 | 2027-03-31 | 365 | under project mode
ISTS connected IPPS Units
1 | ITPCL TPP | 1 | 600 | 2026-06-01 | 2026-06-30 | 30 | AOH |  |  |  | 238th OCC: Unit is under Emergency S/D due to choke in air preheater. IL&FS shall update as the unit from the partial outage is yet to be revived.
2 | MEL | 1 | 150 | 2026-06-01 | 2026-06-09 | 9 | For Annual Inspection of Boiler |  |  |  | 238th OCC: No participation from MEL
3 | PAINAMPURAM TPP (SEIL P-I) | 2 | 660 | 2026-06-20 | 2026-07-15 | 26 | AOH | 2026-07-16 | 2026-08-09 | 25 | 238th OCC: SEIL P-I confirmed that they stick on to the actual plan.
4 | MPGL Tuticorin(formerly CEPL) | 2 | 600 | 2026-07-15 | 2026-08-29 | 46 | COH | 2027-07-01 | 2027-07-15 | 15 | 238th OCC: MPGL confirmed that they stick on to the revised proposal from 01st July for 15 days.

## AP
Unit Outages to be discussed (April to June 2026)
2026-04-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-05-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-06-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | Dr. N.TATA RAO TPS | 5 | 210 | 2026-06-15 | 2026-06-30 | 16 | Annual Overhaul
2 | Dr. N.TATA RAO TPS | 3 | 210 | 2026-06-20 | 2026-07-05 | 16 | Annual Overhaul

## TS
Unit Outages to be discussed (April to June 2026)
2026-04-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-05-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-06-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | KAKATIYA TPS | 1 | 500 | 2026-06-01 | 2026-07-15 | 45 | COH
2 | SINGARENI TPP | 2 | 600 | 2026-06-16 | 2026-07-21 | 36 | AOH
3 | BHADRADRI TPP | 1 | 270 | 2026-06-18 | 2026-07-07 | 20 | AOH

## KAR
Unit Outages to be discussed (April to June 2026)
2026-04-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | RAICHUR TPS | 1 | 210 | 2026-04-01 | 2027-03-31 | 365 | Long shut down
2026-05-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-06-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | BELLARY TPS | 2 | 500 | 2026-06-01 | 2026-07-31 | 61 | COH/ RLA of TG
2 | RAICHUR TPS | 3 | 210 | 2026-06-01 | 2026-09-19 | 111 | R & M of Turbine & Generator and MOH
3 | TORANGALLU TPS(SBU-I) | 1 | 130 | 2026-06-03 | 2026-06-17 | 15 | AOH
4 | TORANGALLU TPS(SBU-II) | 3 | 300 | 2026-06-10 | 2026-11-27 | 171 | Boiler R&M works & COH
5 | YERMARUS TPP | 1 | 800 | 2026-06-11 | 2026-07-10 | 30 | AOH
6 | TORANGALLU TPS(SBU-II) | 4 | 300 | 2026-06-18 | 2026-07-02 | 15 | AOH

## TN
Unit Outages to be discussed (April to June 2026)
2026-04-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-05-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-06-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NEYVELI TPS(Z) | 1 | 250 | 2026-06-02 | 2026-06-07 | 6 | R&M activities
2 | VALUTHUR CCPP | 4 | 32.4 | 2026-06-05 | 2026-06-14 | 10 | Renewal of Boiler Licence and Its allied works of HRSG

## PUDU
Unit Outages to be discussed (April to June 2026)
2026-04-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-05-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | NIL
2
2026-06-01
|  |  |  | Approved by MoP/CEA |  |  |  | Updated Plan /Actual Availed
S No. | Station | Unit | MW | From | To | No. of Days | Reason | From | To | No. of Days | Reason | Remarks
1 | KARAIKAL CCPP | 1 | 32.5 | 2026-06-02 | 2026-06-13 | 12 | Boiler License Renewal