## Gantt Tracker
IEGC 2023 — Generator Test Schedule Tracker ¦ Southern Region ¦ FY 2024-25 to 2028-29
|  |  |  | FY 2024-25 |  |  | FY 2025-26 |  |  | FY 2026-27 |  |  | FY 2027-28 |  |  | FY 2028-29
Generator | Utility | Fuel | MW | Tests Due | Status | Month / Note | Tests Due | Status | Month / Note | Tests Due | Status | Month / Note | Tests Due | Status | Month / Note | Tests Due | Status | Month / Note
◆ APGENCO/AP-IPPs
VTPS-1 | APGENCO | Thermal | 210 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | DEC-27 |  |  |  | T5-AGC not available
VTPS-2 | APGENCO | Thermal | 210 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-27 |  |  |  | T5-AGC not available
VTPS-3 | APGENCO | Thermal | 210 | [6 empty] | T4, T5 | SCHEDULED | DEC-26 | T1, T2, T3 | SCHEDULED | DEC-27 |  |  |  | T5-AGC not available
VTPS-4 | APGENCO | Thermal | 210 | [6 empty] | T4, T5 | SCHEDULED | NOV-26 | T1, T2, T3 | SCHEDULED | NOV-27 |  |  |  | T5-AGC not available
VTPS-5 | APGENCO | Thermal | 210 | [6 empty] | T1, T2, T3 | SCHEDULED | JUL-26 | T4, T5 | SCHEDULED | JUL-27 |  |  |  | T5-AGC not available
VTPS-6 | APGENCO | Thermal | 210 |  |  |  | T1, T2, T3 | SCHEDULED | SEP-25 |  |  |  | T4, T5 | SCHEDULED | SEP-27 |  |  |  | T5-AGC not available
VTPS-7 | APGENCO | Thermal | 500 |  |  |  | T1, T2, T3 | SCHEDULED | JUN-25 | T4, T5 | SCHEDULED | JUN-26 | [6 empty] | T5-AGC not available
VTPS-8 | APGENCO | Thermal | 800 | [6 empty] | T1, T2, T3, T4, T5 | SCHEDULED | AUG-26 | [6 empty] | T5-AGC not available
RTPP Stage 1 U-1 | APGENCO | Thermal | 210 | [6 empty] | T1, T2 | SCHEDULED | APR-26 | T3 | SCHEDULED | MAY-27 | T4, T5 | SCHEDULED | JUN-28 | T5-AGC not available
RTPP Stage 1 U-2 | APGENCO | Thermal | 210 | [6 empty] | T1, T2 | SCHEDULED | APR-26 | T3 | SCHEDULED | MAY-27 | T4, T5 | SCHEDULED | JUN-28 | T5-AGC not available
RTPP Stage 2 U-3 | APGENCO | Thermal | 210 | [6 empty] | T1, T2 | SCHEDULED | APR-26 | T3 | SCHEDULED | MAY-27 | T4, T5 | SCHEDULED | JUN-28 | T5-AGC not available
RTPP Stage 2 U-4 | APGENCO | Thermal | 210 | [6 empty] | T1, T2 | SCHEDULED | APR-26 | T3 | SCHEDULED | MAY-27 | T4, T5 | SCHEDULED | JUN-28 | T5-AGC not available
RTPP Stage 3 U-5 | APGENCO | Thermal | 210 | [6 empty] | T1, T2 | SCHEDULED | APR-26 | T3 | SCHEDULED | MAY-27 | T4, T5 | SCHEDULED | JUN-28 | T5-AGC not available
RTPP Stage 4 U-6 | APGENCO | Thermal | 600 | [6 empty] | T1, T2 | SCHEDULED | APR-26 | T3 | SCHEDULED | MAY-27 | T4, T5 | SCHEDULED | JUN-28 | T5-AGC not available
Krishnapatnam U-1 | APGENCO | Thermal | 800 |  |  |  | T1, T2, T3, T4, T5 | SCHEDULED | (T5)JUL-AUG 25 & (T1-4)OCT-NOV 25
Krishnapatnam U-2 | APGENCO | Thermal | 800 |  |  |  | T1, T2, T3, T4, T5 | SCHEDULED | (T5)JUL-AUG 25 & (T1-4)OCT-NOV 25
Krishnapatnam U-3 | APGENCO | Thermal | 800 | T3 | SCHEDULED | OCT-24 | T1, T2, T4, T5 | SCHEDULED | (T5)JUL-AUG 25 & (T1,2,4)OCT-NOV 25 | [9 empty] | T5-AGC not available
Upper Sileru-1 | APGENCO | Hydro | 60 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | SEP-27 |  |  |  | T5-AGC not available
Upper Sileru-2 | APGENCO | Hydro | 60 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | SEP-27 |  |  |  | T5-AGC not available
Upper Sileru-3 | APGENCO | Hydro | 60 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | OCT-27 |  |  |  | T5-AGC not available
Upper Sileru-4 | APGENCO | Hydro | 60 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | OCT-27 |  |  |  | T5-AGC not available
Donkarayi | APGENCO | Hydro | 25 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 28 | T5-AGC not available
Lower Sileru-1 | APGENCO | Hydro | 115 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Lower Sileru-2 | APGENCO | Hydro | 115 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Lower Sileru-3 | APGENCO | Hydro | 115 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 28 | T5-AGC not available
Lower Sileru-4 | APGENCO | Hydro | 115 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 28 | T5-AGC not available
Srisailam RB-1 | APGENCO | Hydro | 110 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Srisailam RB-2 | APGENCO | Hydro | 110 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Srisailam RB-3 | APGENCO | Hydro | 110 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Srisailam RB-4 | APGENCO | Hydro | 110 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Srisailam RB-5 | APGENCO | Hydro | 110 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 28 | T5-AGC not available
Srisailam RB-6 | APGENCO | Hydro | 110 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 28 | T5-AGC not available
Srisailam RB-7 | APGENCO | Hydro | 110 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 28 | T5-AGC not available
Nagarjunsagar RH-1 | APGENCO | Hydro | 30 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Nagarjunsagar RH-2 | APGENCO | Hydro | 30 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Nagarjunsagar RH-3 | APGENCO | Hydro | 30 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Nagarjunasagar Tail Pond HES 1 | APGENCO | Hydro | 25 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Nagarjunasagar Tail Pond HES 2 | APGENCO | Hydro | 25 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | NOV-DEC 27 |  |  |  | T5-AGC not available
Lanco Stage-2 | AP IPP | IPP | 112
HNPCL (Hinduja) - U1 | AP IPP | IPP | 520
HNPCL (Hinduja) - U2 | AP IPP | IPP | 520
◆ TGGENCO/TG-IPPs
KTPS-9 (Stage V) | TGGENCO | Thermal | 250 | [6 empty] | T1 | SCHEDULED | Aug 2026 |  |  |  | T2, T3, T4 | SCHEDULED | Aug 2028 | T5-AGC not available
KTPS-10 (Stage V) | TGGENCO | Thermal | 250 | [6 empty] | T1 | SCHEDULED | Aug 2026 |  |  |  | T2, T3, T4 | SCHEDULED | Aug 2028 | T5-AGC not available
KTPS-11 (Stage VI) | TGGENCO | Thermal | 500 | T4 | COMPLETED | 2026-03-11 | [6 empty] | T1, T2, T3, T5 | SCHEDULED | Mar 2028
KTPS-12 (Stage VII) | TGGENCO | Thermal | 800 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | Oct 2028
KTPP Unit-1 | TGGENCO | Thermal | 500 | [6 empty] | T1, T2, T3, T4, T5 | SCHEDULED | Jan-Feb 2027 | [6 empty] | T5-AGC not available
KTPP Unit-2 | TGGENCO | Thermal | 600 | [6 empty] | T1, T2, T3, T4 | SCHEDULED | Jan-Feb 2027 | [6 empty] | T5-AGC not available
BTPS U-1 | TGGENCO | Thermal | 270 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | Aug-Sep 2027
BTPS U-2 | TGGENCO | Thermal | 270 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | Aug-Sep 2027
BTPS U-3 | TGGENCO | Thermal | 270 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | Aug-Sep 2027
BTPS U-4 | TGGENCO | Thermal | 270 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | Aug-Sep 2027
Srisailam LB-1 | TGGENCO | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | (T1,T2,T3)Jun-28, (T4,T5) Apr-28
Srisailam LB-2 | TGGENCO | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | (T1,T2,T3)Jun-28, (T4,T5) Apr-28
Srisailam LB-3 | TGGENCO | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | (T1,T2,T3)Jun-28, (T4,T5) Apr-28
Srisailam LB-4 | TGGENCO | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | (T1,T2,T3)Jun-28, (T4,T5) Apr-28
Srisailam LB-5 | TGGENCO | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | (T1,T2,T3)Jun-28, (T4,T5) Apr-28
Srisailam LB-6 | TGGENCO | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | (T1,T2,T3)Jun-28, (T4,T5) Apr-28
Nagarjunsagar-1 | TGGENCO | Hydro | 110 |  |  |  | T3 | SCHEDULED | 2025-09-14 | [6 empty] | T1, T2, T4, T5 | SCHEDULED | Oct 2028
Nagarjunsagar-2 | TGGENCO | Hydro | 100.8 | [6 empty] | T3 | SCHEDULED | Aug 2026 |  |  |  | T1, T2, T4, T5 | SCHEDULED | Oct 2028
Nagarjunsagar-3 | TGGENCO | Hydro | 100.8 | [6 empty] | T3 | SCHEDULED | Aug 2026 |  |  |  | T1, T2, T4, T5 | SCHEDULED | Oct 2028
Nagarjunsagar-4 | TGGENCO | Hydro | 100.8 | [6 empty] | T3 | SCHEDULED | Aug 2026 |  |  |  | T1, T2, T4, T5 | SCHEDULED | Oct 2028
Nagarjunsagar-5 | TGGENCO | Hydro | 110 | [6 empty] | T3 | SCHEDULED | Aug 2026 |  |  |  | T1, T2, T4, T5 | SCHEDULED | Oct 2028
Nagarjunsagar-6 | TGGENCO | Hydro | 100.8 | [6 empty] | T3 | SCHEDULED | Aug 2026 |  |  |  | T1, T2, T4, T5 | SCHEDULED | Oct 2028
Nagarjunsagar-7 | TGGENCO | Hydro | 100.8 | [6 empty] | T3 | SCHEDULED | Aug 2026 |  |  |  | T1, T2, T4, T5 | SCHEDULED | Oct 2028
Nagarjunsagar-8 | TGGENCO | Hydro | 100.8 | [6 empty] | T3 | SCHEDULED | Aug 2026 |  |  |  | T1, T2, T4, T5 | SCHEDULED | Oct 2028
Nagarjunsagar LH-1 | TGGENCO | Hydro | 30 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Nagarjunsagar LH-2 | TGGENCO | Hydro | 30 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Priyadarsini Jurala-1 | TGGENCO | Hydro | 39 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Priyadarsini Jurala-2 | TGGENCO | Hydro | 39 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Priyadarsini Jurala-3 | TGGENCO | Hydro | 39 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Priyadarsini Jurala-4 | TGGENCO | Hydro | 39 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Priyadarsini Jurala-5 | TGGENCO | Hydro | 39 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Priyadarsini Jurala-6 | TGGENCO | Hydro | 39 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Lower Jurala-1 | TGGENCO | Hydro | 40 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Lower Jurala-2 | TGGENCO | Hydro | 40 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Lower Jurala-3 | TGGENCO | Hydro | 40 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Lower Jurala-4 | TGGENCO | Hydro | 40 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Lower Jurala-5 | TGGENCO | Hydro | 40 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Lower Jurala-6 | TGGENCO | Hydro | 40 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Pulichintala Unit - 1 | TGGENCO | Hydro | 30 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Pulichintala Unit - 2 | TGGENCO | Hydro | 30 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Pulichintala Unit - 3 | TGGENCO | Hydro | 30 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
Pulichintala Unit - 4 | TGGENCO | Hydro | 30 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2028-11-01
STPP Unit - 1, Singareni | TG IPP | IPP | 600
STPP Unit - 2, Singareni | TG IPP | IPP | 600
◆ KPCL/Kar-IPPs
Raichur TPS U-1 | KPCL | Thermal | 210 | [15 empty] | Under long shut down. Proposed in 2029-30.
Raichur TPS U-2 | KPCL | Thermal | 210 | T4 | COMPLETED | 2024-04-08 |  |  |  | T1, T2, T3, T5 | SCHEDULED
Raichur TPS U-3 | KPCL | Thermal | 210 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Raichur TPS U-4 | KPCL | Thermal | 210 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Raichur TPS U-5 | KPCL | Thermal | 210 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Raichur TPS U-6 | KPCL | Thermal | 210 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Raichur TPS U-7 | KPCL | Thermal | 210 | [6 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Raichur TPS U-8 | KPCL | Thermal | 250 | [6 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Bellary TPS U-1 | KPCL | Thermal | 500 |  |  |  | T4 | COMPLETED | 2025-08-12 | T1, T2, T3, T5 | SCHEDULED
Bellary TPS U-2 | KPCL | Thermal | 500 | T4 | COMPLETED | 2024-04-08 |  |  |  | T1, T2, T3, T4, T5 | SCHEDULED
Bellary TPS U-3 | KPCL | Thermal | 700 | [6 empty] | T3 | SCHEDULED | 02-Apr-26
YTPS Yermarus U-1 | KPCL | Thermal | 800 | T4 | COMPLETED | 2025-08-14 |  |  |  | T1, T2, T3, T5 | SCHEDULED | [7 empty] | T5-AGC not available
YTPS Yermarus U-2 | KPCL | Thermal | 800 | [6 empty] | T1, T2, T3, T4, T5 | SCHEDULED | [7 empty] | T5-AGC not available
Sharavati-1 | KPCL | Hydro | 103.5 | [6 empty] | T4 | SCHEDULED | planned for 1 unit | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-2 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-3 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-4 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-5 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-6 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-7 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-8 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-9 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Sharavati-10 | KPCL | Hydro | 103.5 | [9 empty] | T1, T2, T3 | SCHEDULED |  |  |  |  | T5-AGC not in service
Linganamakki-1 | KPCL | Hydro | 27.5 | [6 empty] | T1, T2,T3, T4, T5 | SCHEDULED
Linganamakki-2 | KPCL | Hydro | 27.5 | [6 empty] | T1, T2,T3, T4, T5 | SCHEDULED
Nagjhari-1 | KPCL | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Nagjhari-2 | KPCL | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Nagjhari-3 | KPCL | Hydro | 150 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Nagjhari-4 | KPCL | Hydro | 150 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Nagjhari-5 | KPCL | Hydro | 150 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Nagjhari-6 | KPCL | Hydro | 135 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Supa-1 | KPCL | Hydro | 50 | [6 empty] | T1, T2,T3, T4, T5 | SCHEDULED
Supa-2 | KPCL | Hydro | 50 | [6 empty] | T1, T2,T3, T4, T5 | SCHEDULED
VUGPH-1 | KPCL | Hydro | 115 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED
VUGPH-2 | KPCL | Hydro | 115 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED
VUGPH-3 | KPCL | Hydro | 115 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED
VUGPH-4 | KPCL | Hydro | 115 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED
Kadra-1 | KPCL | Hydro | 50 |  |  |  | T1, T2, T3 | SCHEDULED | FY 25-26
Kadra-2 | KPCL | Hydro | 50 |  |  |  | T1, T2, T3 | SCHEDULED | FY 25-26
Kadra-3 | KPCL | Hydro | 50 |  |  |  | T1, T2, T3 | SCHEDULED | FY 25-26
Kodasalli-1 | KPCL | Hydro | 40 |  |  |  | T1, T2, T3 | SCHEDULED | FY 25-26
Kodasalli-2 | KPCL | Hydro | 40 |  |  |  | T1, T2, T3 | SCHEDULED | FY 25-26
Kodasalli-3 | KPCL | Hydro | 40 |  |  |  | T1, T2, T3 | SCHEDULED | FY 25-26
Gerasoppa STR-1 | KPCL | Hydro | 60 |  |  |  | T1, T2 | COMPLETED | 2026-05-08 | T3 | SCHEDULED |  | T4 | SCHEDULED |  |  |  |  | T5-AGC not in service
Gerasoppa STR-2 | KPCL | Hydro | 60 |  |  |  | T1, T2 | COMPLETED | 2026-05-09 | T3 | SCHEDULED |  | T4 | SCHEDULED |  |  |  |  | T5-AGC not in service
Gerasoppa STR-3 | KPCL | Hydro | 60 |  |  |  | T1, T2 | COMPLETED | 2026-05-06 | T3 | SCHEDULED |  |  |  |  | T4 | SCHEDULED |  | T5-AGC not in service
Gerasoppa STR-4 | KPCL | Hydro | 60 | [6 empty] | T3 | SCHEDULED |  |  |  |  | T4 | SCHEDULED |  | T5-AGC not in service
Alamatti-1 | KPCL | Hydro | 15
Alamatti-2 | KPCL | Hydro | 55
Alamatti-3 | KPCL | Hydro | 55
Alamatti-4 | KPCL | Hydro | 55
Alamatti-5 | KPCL | Hydro | 55
Alamatti-6 | KPCL | Hydro | 55
JSWEL SBU 1 U1 | Kar IPP | IPP | 130
JSWEL SBU 1 U2 | Kar IPP | IPP | 130
JSWEL SBU 2 U1 | Kar IPP | IPP | 300
JSWEL SBU 2 U2 | Kar IPP | IPP | 300
JSWEL CPP U3 | Kar IPP | IPP | 300
JSWEL CPP U4 | Kar IPP | IPP | 300
UPCL Unit 1 | Kar IPP | IPP | 600 | [6 empty] | T3 | SCHEDULED | 2026-09-01 | T1, T2, T4 | SCHEDULED | 2027-09-01 |  |  |  | T5-FOTE not available
UPCL Unit 2 | Kar IPP | IPP | 600 | [6 empty] | T1, T2, T3, T4 | SCHEDULED | 2026-09-01 | [6 empty] | T5-FOTE not available
◆ KSEBL
Kuttiadi-1 | KSEBL | Hydro | 25 | [6 empty] | T1, T2,T3, T4, T5 | SCHEDULED
Kuttiadi-2 | KSEBL | Hydro | 25 |  |  |  | T1, T2,T3, T4, T5 | SCHEDULED
Kuttiadi-3 | KSEBL | Hydro | 25 | T1, T2,T3, T4, T5 | SCHEDULED
KES (Kuttiadi-4) | KSEBL | Hydro | 50 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
KAES-1 (Kuttiadi-5) | KSEBL | Hydro | 50 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
KAES-2 (Kuttiadi-6) | KSEBL | Hydro | 50 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Neriamangalam Extn. | KSEBL | Hydro | 25 | T1 | SCHEDULED |  | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED
Sabarigiri-1 | KSEBL | Hydro | 55 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T4 | SCHEDULED |  | T5 | SCHEDULED
Sabarigiri-2 | KSEBL | Hydro | 55 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T4 | SCHEDULED |  | T5 | SCHEDULED
Sabarigiri-3 | KSEBL | Hydro | 55 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Sabarigiri-4 | KSEBL | Hydro | 55 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Sabarigiri-5 | KSEBL | Hydro | 60 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Sabarigiri-6 | KSEBL | Hydro | 60 | T1 | SCHEDULED |  | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED
Idukki-1 | KSEBL | Hydro | 130 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T4 | SCHEDULED |  | T5 | SCHEDULED
Idukki-2 | KSEBL | Hydro | 130 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T4 | SCHEDULED |  | T5 | SCHEDULED
Idukki-3 | KSEBL | Hydro | 130 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Idukki-4 | KSEBL | Hydro | 130 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Idukki-5 | KSEBL | Hydro | 130 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Idukki-6 | KSEBL | Hydro | 130 | T1 | SCHEDULED |  | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED
Idamalayar-1 | KSEBL | Hydro | 37.5 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T4 | SCHEDULED |  | T5 | SCHEDULED
Idamalayar-2 | KSEBL | Hydro | 37.5 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T4 | SCHEDULED |  | T5 | SCHEDULED
Lower Periyar-1 | KSEBL | Hydro | 60 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Lower Periyar-2 | KSEBL | Hydro | 60 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Lower Periyar-3 | KSEBL | Hydro | 60 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Kakkad-1 | KSEBL | Hydro | 25 | T1 | SCHEDULED |  | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T5 | SCHEDULED
Kakkad-2 | KSEBL | Hydro | 25 | T1 | SCHEDULED |  | T2 | SCHEDULED |  | T3 | SCHEDULED |  | T4 | SCHEDULED |  | T5 | SCHEDULED
◆ TNPGCL/TNGECL
Tuticorin-1 | TNPGCL | Thermal | 210 | [6 empty] | T1, T2, T3 | SCHEDULED | Nov 2026 | T4, T5 | SCHEDULED | Sep 2027
Tuticorin-2 | TNPGCL | Thermal | 210 | [6 empty] | T1, T2, T3 | SCHEDULED | Oct 2026 | T4, T5 | SCHEDULED | Sep 2027
Tuticorin-3 | TNPGCL | Thermal | 210 | [6 empty] | T1, T2, T3 | SCHEDULED | Oct 2026 | T4, T5 | SCHEDULED | Sep 2027
Tuticorin-4 | TNPGCL | Thermal | 210 | [9 empty] | T1, T2 | SCHEDULED | Jul 2027 | T3, T4, T5 | SCHEDULED | Jan 2029
Tuticorin-5 | TNPGCL | Thermal | 210 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | (T1,T2) Jul-27, (T3,T4,T5) Jan-28
Mettur-1 | TNPGCL | Thermal | 210 | T5 | SCHEDULED | 14-Jul-24 | T5 | SCHEDULED | 15-Jul-25 | T5 | SCHEDULED | 19-Jul-26 | T5 | SCHEDULED | 18-Jul-27 | T1, T2, T3, T5 | SCHEDULED | 2028 + Jan-29 | T4&T5-LMV Turnine with Hydrp Mechanical Governing System
Mettur-2 | TNPGCL | Thermal | 210 | T5 | SCHEDULED | 23-Aug-24 | T5 | SCHEDULED | 25-Aug-25 | T3, T5 | SCHEDULED | Apr+Aug 2026 | T5 | SCHEDULED | 25-Aug-27 | T1, T2, T5 | SCHEDULED | 2028 + Jan-29
Mettur-3 | TNPGCL | Thermal | 210 | T5 | SCHEDULED | 29-Jun-24 | T5 | SCHEDULED | 27-Jun-25 | T5 | SCHEDULED | 28-Jun-26 | T3, T5 | SCHEDULED | Dec+Jun 2027 | T1, T2, T5 | SCHEDULED | 2028 + Jan-29
Mettur-4 | TNPGCL | Thermal | 210 | T5 | SCHEDULED | 09-Sep-24 | T5 | SCHEDULED | 07-Sep-25 | T5 | SCHEDULED | 08-Sep-26 | T3, T5 | SCHEDULED | Dec+Sep 2027 | T1, T2, T5 | SCHEDULED | 2028 + Jan-29
Mettur-5 | TNPGCL | Thermal | 600 |  |  |  | T4 | SCHEDULED | 2025-12-01 | T1, T2, T3, T5 | SCHEDULED | 2026-12-01
North Chennai-1 | TNPGCL | Thermal | 210 |  |  |  | T1, T2 | SCHEDULED | Jan 2026 |  |  |  | T3 | SCHEDULED | Jan 2028 | T4, T5 | SCHEDULED | Jan 2029
North Chennai-2 | TNPGCL | Thermal | 210 |  |  |  | T1, T2 | SCHEDULED | Jan 2026 |  |  |  | T3 | SCHEDULED | Jan 2028 | T4, T5 | SCHEDULED | Jan 2029
North Chennai-3 | TNPGCL | Thermal | 210 |  |  |  | T1, T2 | SCHEDULED | Jan 2026 |  |  |  | T3 | SCHEDULED | Jan 2028 | T4, T5 | SCHEDULED | Jan 2029
North Chennai-4 | TNPGCL | Thermal | 600 | [6 empty] | T1, T2 | SCHEDULED | Nov 2026 | T3 | SCHEDULED | Nov 2027 | T4, T5 | SCHEDULED | Nov 2028
North Chennai-5 | TNPGCL | Thermal | 600 | [6 empty] | T1, T2 | SCHEDULED | Sep 2026 | T3 | SCHEDULED | Sep 2027 | T4, T5 | SCHEDULED | Sep 2028
Kunda-PH 1 Unit 1 | TNGECL | Hydro | 20
Kunda-PH 1 Unit 2 | TNGECL | Hydro | 20
Kunda-PH 1 Unit 3 | TNGECL | Hydro | 20
Kunda-PH 2 Unit 1 | TNGECL | Hydro | 35
Kunda-PH 2 Unit 2 | TNGECL | Hydro | 35
Kunda-PH 2 Unit 3 | TNGECL | Hydro | 35
Kunda-PH 2 Unit 4 | TNGECL | Hydro | 35
Kunda-PH 2 Unit 5 | TNGECL | Hydro | 35
Kunda-PH 3 Unit 1 | TNGECL | Hydro | 60
Kunda-PH 3 Unit 2 | TNGECL | Hydro | 60
Kunda-PH 3 Unit 3 | TNGECL | Hydro | 60
Kunda-PH 4 Unit 1 | TNGECL | Hydro | 50
Kunda-PH 4 Unit 2 | TNGECL | Hydro | 50
Kunda-PH 5 Unit 1 | TNGECL | Hydro | 20
Kunda-PH 5 Unit 2 | TNGECL | Hydro | 20
Kunda-PH 6 Unit 1 | TNGECL | Hydro | 30
Suruliar-1 | TNGECL | Hydro | 35
Kadamparai-1 | TNGECL | Hydro | 100
Kadamparai-2 | TNGECL | Hydro | 100
Kadamparai-3 | TNGECL | Hydro | 100
Kadamparai-4 | TNGECL | Hydro | 100
Aliyar | TNGECL | Hydro | 60
PUSHEP PH-1 | TNGECL | Hydro | 50
PUSHEP PH-2 | TNGECL | Hydro | 50
PUSHEP PH-3 | TNGECL | Hydro | 50
Mettur Dam (4x12.5) | TNGECL | Hydro
Mettur Dam (4x12.5)-U3 | TNGECL | Hydro | 12.5
Mettur Tunnel PH-1 | TNGECL | Hydro | 50
Mettur Tunnel PH-2 | TNGECL | Hydro | 50
Mettur Tunnel PH-3 | TNGECL | Hydro | 50
Mettur Tunnel PH-4 | TNGECL | Hydro | 50
Sarkarpathy | TNGECL | Hydro | 30
Sholayar-Stg 1, Unit 1 | TNGECL | Hydro | 42
Sholayar-Stg 1, Unit 2 | TNGECL | Hydro | 42
Sholayar-2 | TNGECL | Hydro | 25
Kodayar-1 | TNGECL | Hydro | 60
Kodayar-2 | TNGECL | Hydro | 40
Suruliyar | TNGECL | Hydro | 35
LMHEP-Barrage-1 | TNGECL | Hydro | 30
LMHEP-Barrage-2 | TNGECL | Hydro | 30
LMHEP-Barrage-3 | TNGECL | Hydro | 30
LMHEP-Barrage-4 | TNGECL | Hydro | 30
Bhavani Kattalai PH - 1 | TNGECL | Hydro | 30
Bhavani Kattalai PH - 2 | TNGECL | Hydro | 30
Bhavani Kattalai PH - 3 | TNGECL | Hydro | 30
Parson valley (1 * 30) | TNGECL | Hydro | 30
Periyar-1 | TNGECL | Hydro | 42
Periyar-2 | TNGECL | Hydro | 42
Periyar-3 | TNGECL | Hydro | 42
Periyar-4 | TNGECL | Hydro | 42
Vazhudhur - I | TNPGCL | Gas | 95 | [6 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2027-03-01
Vazhudhur - II | TNPGCL | Gas | 92.2 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2027-07-01
Kuttalam | TNPGCL | Gas | 101 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | 2027-12-01
Neyveli STCMS-1 (TAQA) | TN IPP | IPP | 250
SEPC | TN IPP | IPP | 525
◆ CGS
RSTPS-1 | CGS | Thermal | 200 | T1, T3, T4 | SCHEDULED |  | T2 | SCHEDULED |  | T5 | SCHEDULED
RSTPS-2 | CGS | Thermal | 200 | T1, T3, T4 | SCHEDULED |  | T2 | SCHEDULED |  | T5 | SCHEDULED
RSTPS-3 | CGS | Thermal | 200 | T1, T3, T4 | SCHEDULED |  | T2 | SCHEDULED |  | T5 | SCHEDULED
RSTPS-4 | CGS | Thermal | 500 | T1, T4, T5 | SCHEDULED |  | T2, T3 | SCHEDULED
RSTPS-5 | CGS | Thermal | 500 | T1, T4, T5 | SCHEDULED |  | T2, T3 | SCHEDULED
RSTPS-6 | CGS | Thermal | 500 | T1, T4, T5 | SCHEDULED |  | T2, T3 | SCHEDULED
RSTPS-7 | CGS | Thermal | 500 | T1, T3, T4, T5 | SCHEDULED |  | T2 | SCHEDULED
Talcher Stage II-3 | CGS | Thermal | 500 |  |  |  | T1, T2, T3 | SCHEDULED
Talcher Stage II-4 | CGS | Thermal | 500 |  |  |  | T1, T2, T3 | SCHEDULED
Talcher Stage II-5 | CGS | Thermal | 500 | [9 empty] | T1, T2, T3 | SCHEDULED
Talcher Stage II-6 | CGS | Thermal | 500 |  |  |  | T1, T2, T3 | SCHEDULED
Simhadri-1 | CGS | Thermal | 500 | T3 | SCHEDULED |  | T5 | SCHEDULED |  | T1 | SCHEDULED |  |  |  |  | T4 | SCHEDULED
Simhadri-2 | CGS | Thermal | 500 |  |  |  | T2, T5 | SCHEDULED | [7 empty] | T4 | SCHEDULED
Simhadri-3 | CGS | Thermal | 500 | T3 | SCHEDULED |  |  |  |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Simhadri-4 | CGS | Thermal | 500 |  |  |  | T2 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED
Kudgi Unit-1 | CGS | Thermal | 800 | T1, T2, T4 | SCHEDULED |  | T5 | SCHEDULED |  | T3 | SCHEDULED
Kudgi Unit-2 | CGS | Thermal | 800 | T1 | SCHEDULED |  | T5 | SCHEDULED |  | T2, T3, T4 | SCHEDULED
Kudgi Unit-3 | CGS | Thermal | 800 | T1, T2, T4 | SCHEDULED |  | T5 | SCHEDULED |  | T3 | SCHEDULED
Telangana STPP Ph-I U-1 | CGS | Thermal | 800 | T4 | COMPLETED | 2026-02-18 | T1, T2, T3, T5 | SCHEDULED
Telangana STPP Ph-I U-2 | CGS | Thermal | 800 | T1, T2, T3, T4, T5 | SCHEDULED | [10 empty] | T1, T2, T3, T4 | SCHEDULED
NTECL Vallur U-1 | CGS | Thermal | 500 | T1, T2 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED |  |  |  |  | T3 | SCHEDULED
NTECL Vallur U-2 | CGS | Thermal | 500 | T1, T2 | SCHEDULED |  | T5 | SCHEDULED |  | T4 | SCHEDULED |  |  |  |  | T3 | SCHEDULED
NTECL Vallur U-3 | CGS | Thermal | 500 |  |  |  | T1, T2, T5 | SCHEDULED |  | T4 | SCHEDULED |  | T3 | SCHEDULED
NLC TS II-1 | CGS | Thermal | 210 | T1, T2, T3 | SCHEDULED | Nov-24 | T4, T5 | SCHEDULED
NLC TS II-2 | CGS | Thermal | 210 | T1, T2, T3 | SCHEDULED | Sep-24 | T4, T5 | SCHEDULED
NLC TS II-3 | CGS | Thermal | 210 | T1, T2, T3 | SCHEDULED | Jan-25 |  |  |  | T4, T5 | SCHEDULED
NLC TS II-4 | CGS | Thermal | 210 |  |  |  | T1, T2, T3 | SCHEDULED | Apr-25 | T4, T5 | SCHEDULED
NLC TS II-5 | CGS | Thermal | 210 |  |  |  | T1, T2, T3 | SCHEDULED | May-25 | T4, T5 | SCHEDULED
NLC TS II-6 | CGS | Thermal | 210 |  |  |  | T1, T2, T3, T4, T5 | SCHEDULED | Jun-25
NLC TS II-7 | CGS | Thermal | 210 |  |  |  | T1, T2, T3, T4, T5 | SCHEDULED | Jul-25
Neyvely TS l Expn : Unit-1 | CGS | Thermal | 210 |  |  |  | T3 | SCHEDULED | Jul-25
Neyvely TS l Expn : Unit-2 | CGS | Thermal | 210 | [9 empty] | T3 | SCHEDULED | 2028-07-01
Neyvely TS 2 Expn : Unit-1 | CGS | Thermal | 250 |  |  |  | T3 | SCHEDULED | 2025-08-01
Neyvely TS 2 Expn : Unit-2 | CGS | Thermal | 250 | [6 empty] | T3 | SCHEDULED
NTPL Unit-1 | CGS | Thermal | 500 | [6 empty] | T1, T2, T3, T4, T5 | SCHEDULED
NTPL Unit-2 | CGS | Thermal | 500 | [6 empty] | T1, T2, T3, T4, T5 | SCHEDULED
NNTPP Unit-1 | CGS | Thermal | 500 |  |  |  | T1 | SCHEDULED | 2025-09-01 | T2 | SCHEDULED | 2026-09-01 | T3 | SCHEDULED
NNTPP Unit-2 | CGS | Thermal | 500 |  |  |  | T1 | SCHEDULED | 2025-10-01 | T2 | SCHEDULED | 2026-10-01 | T3 | SCHEDULED
MAPS Unit-1 | CGS | Nuclear | 220
MAPS Unit-2 | CGS | Nuclear | 220
KAIGA Unit-1 | CGS | Nuclear | 220
KAIGA Unit-2 | CGS | Nuclear | 220
KAIGA Unit-3 | CGS | Nuclear | 220
KAIGA Unit-4 | CGS | Nuclear | 220
KKNPP Unit-1 | CGS | Nuclear | 1000 | [6 empty] | T3 | SCHEDULED | 2027-02-01
KKNPP Unit-2 | CGS | Nuclear | 1000 |  |  |  | T3 | SCHEDULED | 2025-12-01
◆ ISTS IPP
MEL Unit-1 | ISTS IPP | Thermal | 150
MEL Unit-2 | ISTS IPP | Thermal | 150
SEL Unit-1 | ISTS IPP | Thermal | 150
SEL Unit-2 | ISTS IPP | Thermal | 150
SEL Unit-3 | ISTS IPP | Thermal | 150
SEL Unit-4 | ISTS IPP | Thermal | 150
SEIL P-I U-1 | ISTS IPP | Thermal | 660 | [9 empty] | T3, T4 | SCHEDULED | Jan/Mar 28 | T1, T2, T5 | SCHEDULED | Aug/Nov 28
SEIL P-I U-2 | ISTS IPP | Thermal | 660 | [9 empty] | T3, T4 | SCHEDULED | Jan/Mar 28 | T1, T2, T5 | SCHEDULED | Aug/Nov 28
SEIL P-II U-1 | ISTS IPP | Thermal | 660 | [9 empty] | T3, T4 | SCHEDULED | Jan/Mar 28 | T1, T2, T5 | SCHEDULED | May/Jun 28
SEIL P-II U-2 | ISTS IPP | Thermal | 660 | [9 empty] | T3, T4 | SCHEDULED | Jan/Mar 28 | T1, T2, T5 | SCHEDULED | May/Jun 28
IL&FS Unit-1 | ISTS IPP | Thermal | 600 | [9 empty] | T1, T2, T3, T4, T5 | SCHEDULED | Dec 2026
IL&FS Unit-2 | ISTS IPP | Thermal | 600 | [12 empty] | T1, T2, T3, T4, T5 | SCHEDULED | May 2028
CEPL Unit-1 | ISTS IPP | Thermal | 600 | [6 empty] | T1, T2, T3, T4 | SCHEDULED | (T1,T2,T4) Feb-27, (T3)-Jul-26 | [6 empty] | T5-FOTE not Available for state network connetivity
CEPL Unit-2 | ISTS IPP | Thermal | 600 | [6 empty] | T1, T2, T4 | SCHEDULED | 2026-09-01 |  |  |  | T3 | SCHEDULED | 2028-06-01 | T5-FOTE not Available for state network connetivity
Lanco Ph-II Unit-1 | ISTS IPP | Thermal | 233
Lanco Ph-II Unit-2 | ISTS IPP | Thermal | 133